## OLD_AugustGuess
version	features/aims	JIRA based Guess dev days	notes	DEV day total	human date guess

“1.1.1”	Core functionality	0
“1.1.2”	Registry/Billing	0	should be zero (all closed in atlassian)...needs updating
1.1.1a	Core functionality	6	all testing time only. Maybe 60% of this testing could be done by non-dev team. Can also be done in parallel	6	parallel work can happen while we do other tasks?
1.1.1b	Stability and core features	11.2		17.2	09/09/12
1.1.1c	Stability and core features	16.675		33.875	20/09/12
1.1.1d	Data extraction module/functionality	40		73.875	20/10/12
1.1.1e	Getting prod env ready and transfering WAGER data/setting/ldap to prod	44	the more hands on deck testing: the less dev time for this.	117.875	20/11/12	this magical number allows for very little testing really...or for the inevitable bugs picked up in testing. The more help we get from now until the release day, the better to make sure peoples data is going to be as expected

“1.1.3”	Geneological Family etc, base strutcture, data transfer and visualisation	60	40 days is our guess for base structure and importing data. Crazy loose guess at 20 days for some kind of linking to a visualisation solution	177.875	07/01/13	Trav will be away about 4 weeks, but could do some work remotely. Plus whatever holidays everyone else takes

“1.1.5”	Genotypic basic linking, storage and/or execution	50	mad guess...depends what is required	227.875	12/02/13	depends on trav & thilinas hours per week...the estimate its so crass given what is required is very undefined right now
“1.1.6”	Enhanced data linkage and reporting	40	I wont even claim to have a decent guess at this...jsut throwing a number out there... what is this?	267.875	10/03/13	guesses are starting to get meaningless
“2.0.0”	feature requests and things like test scripts	56	this stuff may sneak up???	323.875	20/04/13
“3.0.0”	optomistic feature requests	16	this stuff may sneak up???	339.875	01/05/13
1.1.1b-admin	admin tasks not for developers	n\a	hopefully this is parallel to development	339.875	n/a
“1.1.4”	OLD Data extraction module/functionality project	ZERO...moved up above to make logical order		n/a

## OLD_PedB4Prd
THIS VERSION IS PUTTING PEDIGREE BEFORE PROD RELEASE TO MEET FUNDING DEADLINES
version	features/aims	Atlassian Estimates based Guess in dev days	notes	DEV day total	human date guess

“1.1.1”	Core functionality	0
“1.1.2”	Registry/Billing	0	should be zero (all closed in atlassian)...needs updating
1.1.1a	Core functionality	6	all testing time only. Maybe 60% of this testing could be done by non-dev team. Can also be done in parallel	6	parallel work can happen while we do other tasks?
1.1.1b	Stability and core features	9.75		15.75	11/09/12
1.1.1c	Stability and core features	16.675		32.425	20/09/12
1.1.1d	Data extraction module/functionality	40		72.425	20/10/12
“1.1.5”	Genotypic basic linking, storage and/or execution	50	mad guess...depends what is required	122.425	23/11/12	depends on trav & thilinas hours per week...the estimate its so crass given what is required is very undefined right now
1.1.1e	Getting prod env ready and transfering WAGER data/setting/ldap to prod	44	the more hands on deck testing: the less dev time for this.	166.425	06/01/13	this magical number allows for very little testing really...or for the inevitable bugs picked up in testing. The more help we get from now until the release day, the better to make sure peoples data is going to be as expected	Could sneak in before Xmas break, might sneak in after???

“1.1.5”	Genotypic basic linking, storage and/or execution	50	mad guess...depends what is required	216.425	12/02/13	depends on trav & thilinas hours per week...the estimate its so crass given what is required is very undefined right now
“1.1.6”	Enhanced data linkage and reporting	40	I wont even claim to have a decent guess at this...jsut throwing a number out there... what is this?	256.425	10/03/13	guesses are starting to get meaningless
“2.0.0”	feature requests and things like test scripts	56	this stuff may sneak up???	312.425	20/04/13
“3.0.0”	optomistic feature requests	16	this stuff may sneak up???	328.425	01/05/13
1.1.1b-admin	admin tasks not for developers	n\a	hopefully this is parallel to development	328.425	n/a
“1.1.4”	OLD Data extraction module/functionality project	ZERO...moved up above to make logical order		n/a

## quicklyAccross
THIS VERSION IS DISCUSSED WITH PAUL MON 3rd Sept. Aim is to get data across ASAP, and offer support with reports, etc, and in doing so we then figure out extract requirements etc.
version	features/aims	Atlassian based dev days	notes	DEV day total	human date guess

“1.1.1”	Core functionality	0		0
“1.1.2”	Registry/Billing	0		0
1.1.1a	Core functionality	6	all testing time only. Maybe 60% of this testing could be done by non-dev team. Can also be done in parallel	6	10/09/12	let's prioritize this and shut the door...or leave it behind and start testing from scratch?
1.1.1b	Stability and core features	4.5		10.5	10/09/12	Will tee up a build for Saturday night or monday morning
1.1.1c	Stability and core features	25		35.5	08/10/12	Will probably start prior to end of 1.1.1b. Things keep getting added into here...so this date may continue to blow out a little. This date would rely having three developers contributing...else this date would slip a little	We will probably achieve all this if Chris helps a little here and I help a little on his data move
1.1.1e-initialStudy -WARTNOnly	Getting prod env ready and transfering WAGER data/setting/ldap to prod	29	the more hands on deck testing: the less dev time for this. Paul recommends Chris to approach most of this on his own while I continue on coding	64.5	01/11/12	this magical date guess and number allows for very little testing really...or for the inevitable bugs picked up in testing. The more help we get from now until the release day, the better to make sure peoples data is going to be as expected	We will probably achieve all this if Chris helps a little here and I help a little on his data move
1.1.1e-otherStudies	Getting prod env ready and transfering WAGER data/setting/ldap to prod	20	the more hands on deck testing: the less dev time for this. Paul recommends Chris to approach most of this on his own while I continue on coding	84.5	18/11/12	“ “ “ “
1.1.1f	Data extraction module/functionality	40	Travis doing this in parallel with Chris doing the data move	124.5	07/12/12	However trav might be away...so we may just get a first iteration sans bells and whistles before trav departs	This might not happen before trav goes away. Paul has good contingency of report writing going on too. Trav will start this mid-October if not helping Chris...but if he is helping Chris then Chris starts helping on this sooner. Trav will start this mid-November when Trav will be leaving
“1.1.5”	Genotypic basic linking, storage and/or execution	45	mad guess...depends what is required	169.5	10/01/12	depends on everyones hours per week...the estimate its so crass given what is required is very undefined right now...could be 15 days, could be 100. I assume its just storing some meta data and linking some files and storing them in various environments	Trav will be gone most of this. Thilina and Chris can do this while he is gone. If we miss Xmas, it will probably be 10/1/2013, due to 2 weeks of Xmas holidays for all!

“1.1.3”	Geneological / pedigree stuff	60	mad guess...depends what is required. I wont even claim to have a decent guess at this...just throwing a number out there... what is this?	229.5	12/02/13	depends on trav & thilinas hours per week...the estimate its so crass given what is required is very undefined right now

“2.0.0”	feature requests and things like test scripts	56.5	this stuff may sneak up???	286	20/04/13	guesses are starting to get meaningless
“3.0.0”	optomistic feature requests	16	this stuff may sneak up???	302	01/05/13
Unscheduled	Scary bunch of tasks we are not sure about yet	21.5		323.5	?????
1.1.1b-admin	admin tasks not for developers	n\a	hopefully this is parallel to development	323.5	n/a
“1.1.4”	OLD Data extraction module/functionality project	ZERO...moved up above to make logical order		n/a