## Sheet1
Jobs	days a year					% of 1 FTE Yr
	min emergency only	guess at median	max emergency only	min some progress	guess at median	max some progress	min emergency only	guess at median	max emergency only	min some progress	guess at median	max some progress
upgrade underlying DB, software, source control and backup, etc which we run the ark on	10	15	30	14	25	40	4.55	6.82	13.64	6.36	11.36	18.18
server down, external parties messing things up?	5	6	10	5	15	20	2.27	2.73	4.55	2.27	6.82	9.09
24 Builds of code (physical set up transfer plus testing time) - (assume 1 build a month if just emergency fixes)...2 a month for active code base	12	12	36	24	50	72	5.45	5.45	16.36	10.91	22.73	32.73
Take Calls, support, respond and upkeep to jira, management/triage of tasks – proactive / forced training and STRICT guidelines can minimise this. Requirements gathering and business analyst work included	20	50	100	100	120	200	9.09	22.73	45.45	45.45	54.55	90.91
Computer guys doing admin, trying to get money, legal documents, etc. Excludes demos and travelling roadshows	10	10	20	20	25	80	4.55	4.55	9.09	9.09	11.36	36.36
Being IT Guy, consulting our staff, advising, messing with hardware, red box of hard drives, hanging out in server room, etc. Eric determines an amount of this	5	6	20	5	25	100	2.27	2.73	9.09	2.27	11.36	45.45
meetings, overhead, cleaning, answering the door, nonsense, team fun, assorted office tasks and being part of a university	5	10	15	5	10	15	2.27	4.55	6.82	2.27	4.55	6.82
Strictly urgent/emergency/critical - Code Fixes, fix bugs and existing errors & errors caused by the previous list and rushing to make existing code base and generally being a human applying logic in a complex system.	50	100	200	60	120	220	22.73	45.45	90.91	27.27	54.55	100.00	Adding features adds need to bug fix
Bug fixes of slightly less urgent – but still important bugs (eg; has a work around or doesn't affect data integrity...but reflects poorly upon the app or makes things difficult to work with)	0	50	150	50	100	250	0.00	22.73	68.18	22.73	45.45	113.64
New development of more urgent requests necessary to be a consistently usable independent software (auditing, self-testing capability)				50	100	250	0.00	0.00	0.00	22.73	45.45	113.64	it is what we want it to be

General documentation and how-to-demos. Cutting budget here may cost us more in answering support questions	15	15	30	20	30	60	6.82	6.82	13.64	9.09	13.64	27.27
deal with 3rd party coders – both coordination and them messing up.	5	20	30	10	25	50	2.27	9.09	13.64	4.55	11.36	22.73
Live demos and roadshows for prospective and current users	0	10	20	10	30	60	0.00	4.55	9.09	4.55	13.64	27.27
Fancy new stuff or requests we are not convinced of ON DEMAND FOR MONEY. Might not be necessary but great features? money in would determine this...I guess based on consultancy rates or salary paid...this activity can always fill time

Totals thus far	137.0	304.0	661.0	373.0	675.0	1417.0	62.3	138.2	300.5	169.5	306.8	644.1
	assumptions for 'emergency only' median guess requires some strict change of practice;					double check nums:	62.27	138.18	300.45	169.55	306.82	644.09
	if this team is just the ark and just funded by the ark, then they would need to minimize doing everything else
	taking on thrid party assistance comes with strict rules about how to not mess up the core ark project...that's pretty hard to do on a tight budget paying academia
	Assume 220 work days in uni-year...could be more
	Assistance / custom coding / bug fixes are only urgent mistake fixes and vital bug fixes
	training is minimized to where it saves us time fixing things for them – or consultancy based

Jobs	days a year					% of 1 FTE Yr
	min emergency only	guess at median	max emergency only	min some progress	guess at median	max some progress	min emergency only	guess at median	max emergency only	min some progress	guess at median	max some progress
upgrade underlying DB, software, source control and backup, etc which we run the ark on	10	15	30	14	25	40	4.55	6.82	13.64	6.36	11.36	18.18
server down, external parties messing things up?	5	6	10	5	15	20	2.27	2.73	4.55	2.27	6.82	9.09
24 Builds of code (physical set up transfer plus testing time) - (assume 1 build a month if just emergency fixes)...2 a month for active code base	12	12	36	24	50	72	5.45	5.45	16.36	10.91	22.73	32.73
Take Calls, support, respond and upkeep to jira, management/triage of tasks – proactive / forced training and STRICT guidelines can minimise this. Requirements gathering and business analyst work included	20	50	100	100	120	200	9.09	22.73	45.45	45.45	54.55	90.91
Computer guys doing admin, trying to get money, legal documents, etc. Excludes demos and travelling roadshows	10	10	20	20	25	80	4.55	4.55	9.09	9.09	11.36	36.36
Being IT Guy, consulting our staff, advising, messing with hardware, red box of hard drives, hanging out in server room, etc. Eric determines an amount of this	5	6	20	5	25	100	2.27	2.73	9.09	2.27	11.36	45.45
meetings, overhead, cleaning, answering the door, nonsense, team fun, assorted office tasks and being part of a university	5	10	15	5	10	15	2.27	4.55	6.82	2.27	4.55	6.82
Strictly urgent/emergency/critical - Code Fixes, fix bugs and existing errors & errors caused by the previous list and rushing to make existing code base and generally being a human applying logic in a complex system.	50	100	200	60	120	220	22.73	45.45	90.91	27.27	54.55	100.00
Bug fixes of slightly less urgent – but still important bugs (eg; has a work around or doesn't affect data integrity...but reflects poorly upon the app or makes things difficult to work with)	0	50	150	50	100	250	0.00	22.73	68.18	22.73	45.45	113.64
New development of more urgent requests necessary to be a consistently usable independent software (auditing, self-testing capability)				50	100	250	0.00	0.00	0.00	22.73	45.45	113.64

General documentation and how-to-demos. Cutting budget here may cost us more in answering support questions	15	15	30	20	30	60	6.82	6.82	13.64	9.09	13.64	27.27
deal with 3rd party coders – both coordination and them messing up.	5	20	30	10	25	50	2.27	9.09	13.64	4.55	11.36	22.73
Live demos and roadshows for prospective and current users	0	10	20	10	30	60	0.00	4.55	9.09	4.55	13.64	27.27
Fancy new stuff or requests we are not convinced of ON DEMAND FOR MONEY. Might not be necessary but great features? money in would determine this...I guess based on consultancy rates or salary paid...this activity can always fill time

Totals thus far	137.0	304.0	661.0	373.0	675.0	1417.0	62.3	138.2	300.5	169.5	306.8	644.1
	assumptions for 'emergency only' median guess requires some strict change of practice;					double check nums:	62.27	138.18	300.45	169.55	306.82	644.09
	if this team is just the ark and just funded by the ark, then they would need to minimize doing everything else
	taking on thrid party assistance comes with strict rules about how to not mess up the core ark project...that's pretty hard to do on a tight budget paying academia
	Assume 220 work days in uni-year...could be more
	Assistance / custom coding / bug fixes are only urgent mistake fixes and vital bug fixes
	training is minimized to where it saves us time fixing things for them – or consultancy based