## AugustGuess
version	features/aims	Atlassian Estimates based Guess in dev days	notes	DEV day total	human date guess

“1.1.1”	Core functionality	0
“1.1.2”	Registry/Billing	0	should be zero (all closed in atlassian)...needs updating
1.1.1a	Core functionality	6	all testing time only. Maybe 60% of this testing could be done by non-dev team. Can also be done in parallel	6	parallel work can happen while we do other tasks?
1.1.1b	Stability and core features	11.2		17.2	09/09/12
1.1.1c	Stability and core features	16.675		33.875	20/09/12
1.1.1d	Data extraction module/functionality	40		73.875	20/10/12
1.1.1e	Getting prod env ready and transfering WAGER data/setting/ldap to prod	44	the more hands on deck testing: the less dev time for this.	117.875	20/11/12	this magical number allows for very little testing really. The more help we get the better to make sure peoples data is going to be as expected

“1.1.3”	Geneological Family etc, base strutcture, data transfer and visualisation	60	40 days is our guess for base structure and importing data. Crazy loose guess at 20 days for some kind of linking to a visualisation solution	177.875	07/01/12	Trav will be away about 4 weeks, but could do some work remotely. Plus whatever holidays everyone else takes

“2.0.0”	feature requests and things like test scripts	56	this stuff may sneak up???	233.875
“3.0.0”	optomistic feature requests	16	this stuff may sneak up???	249.875
1.1.1b-admin	admin tasks not for developers	n\a	hopefully this is parallel to development	249.875
“1.1.4”	OLD Data extraction module/functionality project	ZERO...moved up above to make logical order		n/a