## Sheet1
modelling Ark's future	description	Min Funding p.a. Req for 1 study	Min funding ph for activity for 1 study	Max Funding p.a. Req for 1 study	Max funding ph for activity for 1 study	Min Funding p.a. Req for 10 studies	Min funding ph for activity for 10 studies	Max Funding p.a. Req for 10 studies	Max funding ph for activity for 10 studies	how should we charge for this?	alternatives
what do we need to finish the ark (to nectar and approx wager specs) and migrate people
requests and bugfixes from lifepool	3-15 days. Not sure how much of that cost we take on	1000		6000		1000		6000
requests and bugfixes other keys uses which are critical to transfer	1-5 months. Hopefully closer to one	9000		50000		9000		50000
further data extraction capabilities	needs about 2-4 develop-months of extras to match wager and have some of the capabilities we are more likely to need. They can get by to some extent with what they currently have and some problem-solving brain power.	20000		40000		25000		50000
migrate all current paying users	Approximately 2-4 developer-weeks for the first study and approximately 2-6 days for each subsequent study PLUS approximately 1-4 tester-months. Third parties could contribute testing or we could use students.	10000		15000		25000		55000
pedigree	I am not sure how much of this cost we bare for Thilina. Plus we also might need me to help push him across the line a little to get anywhere close to deadlines.	?		?		?		?
registry management module and data linkage and reporting module.	just write up and perform some tests...may result in some requirements...3-5 dev weeks estimate	6346.1538461539		10576.9230769231		6346.1538461539		10576.9230769231
genotypic data management capability	this is a grossly generic requirement. If we aim to simply store the file on a file server and perhaps keep minimal metadata initially we will then be meeting nectar requirements, though we will have a long way to go in terms of GOHaD goals and SPArk aims. 1-3 dev months	9166.6666666667		27500		9166.6666666667		27500
source and setup adequate production environment(s) to run all of the studies. Have approx 30-40 active studies and ~30 not used or demos	our existing servers from the NSP (which free to run, may not have adequate power to handle every single study). Alternative servers may be necessary and I guess would be a handy backup in case of disaster. However that does leave us with two instances to support.

totals?		55512.8205128205		149076.923076923		75512.8205128205		199076.923076923			these migration costs are signiificant but so is all of Chris' time and the costs of maintaining hardware...and the liability costs of us being responsible for all of this hardware and the loss of data are high

What The Ark needs to be useful
hosting	free (if nectar approves or self-serviced) else 1000-3000...for more studies, depends if they are willing to share host and database (security and privacy issues may exist)	0		3000		0		20000		People can host their own for free. They can ask Nectar for a free server. If we host it on one of OUR nectar servers/cloud instance, I think we can't ask money for hosting, but that comes down to support money.	We would be opening up a massive can of worms to start hosting and managing software. Only real alternative is we could support people sharing hosting on a commercial platform
code maintenance/bug-fixes that ensure data integrity, security and success of our own and others projects	~50000 for 0.4 of a developer with on costs? This and support could almost be merged to a small extent	50000		110000		110000		170000		A centre cost, with some recovery from charges for other services/support, etc	community coding development. If some of our users have coders, we can use them. I guess we could use students that want to contribute to open source projects pro bono
Free Support and guidance, help	you can choose to offer some base support and guidance or let them roam free – and if they need support pay. Note nectar is funding one full year of support after the final release/sign-off	0		50000		0		110000		A centre cost, with some recovery from charges for other services/support, etc	see below on creating communities and the use of forums
Free Documentation	a minimal set of documentation to set up scenarios and allow as much self help as possible to cut down support costs. Ideally we would like people to be able to take this product and use it in order to have success ourselves. Maybe we can have it such that you cannot download it for free UNTIL you give your details. It at least is something we can collect details on when getting grants, etc.	10000		30000		10000		50000		A centre cost, with some recovery from charges for other services/support, etc

What Extras may people want
improvements of common value	if the centre is able to gain from an improvement which suits a user, it makes sense to contribute to this in some way		65		250		65		250	Charge at cost (~$80 an hour). I would prefer to charge at our minimum cost to get adequate replacements for our lost developer time ($100-150 an hour).	Can just charge at a standard rate of $250 an hour, perhaps with some of discount.
Customized code	– publicly available extention, which we believe will not have wide-spread adoption		65		250		65		65	$250 maybe minus some discount for having it publicly available in case others can use it
Customized code – not available to the public, private use of developer/architect/dba/tester time	private use of developer/architect/dba/tester time		65		250		65		250	whatever our standard rate is, say, $250
Data and Software Architecture advice			65		250		65		250	whatever our standard rate is, say, $250
Data import/Integration/Export/Modification			65		250		65		250	whatever our standard rate is, say, $250
Advanced support			65		250		65		250	whatever our standard rate is, say, $250	we may offer discounts dependent upon tiers of relationships with our users
Some open source groups also offer tested/supported releases beyond whatever is just in the latest code base (could get messy)		30000		110000		110000		220000		I guess this could be more or less like an all around support package which gets you some amount of support, advice, help

What do other open source groups offer;
Some sort of forum for the community to help each other without necessarily getting help from developers/team (though its wise to keep a watch and chime in when necessary)		30000		30000		30000		120000		A centre cost, with some recovery from charges for other services/support, etc. This may save money to keep people helping themselves as much as possible
Perhaps a public list of groups that may be willing to help each other out		0		0		500		1000		A centre cost, with some recovery from charges for other services/support, etc. This may save money to keep people helping themselves as much as possible
Mailing lists for users	recommendations, tips from us – plus they can help out amongst themselves	500		500		500		2000		A centre cost, with some recovery from charges for other services/support, etc. This may save money to keep people helping themselves as much as possible
Mailing list for Developers/contributors	help developers help us	500		500		1000		3000		A centre cost, with some recovery from charges for other services/support, etc. This may save money to keep people helping themselves as much as possible