## AugustGuess
version	features/aims	Atlassian Estimates based Guess in dev days	notes	DEV day total	human date guess

“1.1.1”	Core functionality	0
“1.1.2”	Registry/Billing	0	should be zero (all closed in atlassian)...needs updating
1.1.1a	Core functionality	6	all testing time only. Maybe 60% of this testing could be done by non-dev team. Can also be done in parallel	6	parallel work can happen while we do other tasks?
1.1.1b	Stability and core features	11.2		17.2	09/09/12
1.1.1c	Stability and core features	16.675		33.875	20/09/12
1.1.1d	Data extraction module/functionality	40		73.875	20/10/12
1.1.1e	Getting prod env ready and transfering WAGER data/setting/ldap to prod	44	the more hands on deck testing: the less dev time for this.	117.875	20/11/12	this magical number allows for very little testing really...or for the inevitable bugs picked up in testing. The more help we get from now until the release day, the better to make sure peoples data is going to be as expected

“1.1.3”	Geneological Family etc, base strutcture, data transfer and visualisation	60	40 days is our guess for base structure and importing data. Crazy loose guess at 20 days for some kind of linking to a visualisation solution	177.875	07/01/13	Trav will be away about 4 weeks, but could do some work remotely. Plus whatever holidays everyone else takes

“1.1.5”	Genotypic basic linking, storage and/or execution	50	mad guess...depends what is required	227.875	12/02/13	depends on trav & thilinas hours per week...the estimate its so crass given what is required is very undefined right now
“1.1.6”	Enhanced data linkage and reporting	40	I wont even claim to have a decent guess at this...jsut throwing a number out there... what is this?	267.875	10/03/13	guesses are starting to get meaningless
“2.0.0”	feature requests and things like test scripts	56	this stuff may sneak up???	323.875	20/04/13
“3.0.0”	optomistic feature requests	16	this stuff may sneak up???	339.875	01/05/13
1.1.1b-admin	admin tasks not for developers	n\a	hopefully this is parallel to development	339.875	n/a
“1.1.4”	OLD Data extraction module/functionality project	ZERO...moved up above to make logical order		n/a

## PedB4Prd
THIS VERSION IS PUTTING PEDIGREE BEFORE PROD RELEASE TO MEET FUNDING DEADLINES
version	features/aims	Atlassian Estimates based Guess in dev days	notes	DEV day total	human date guess

“1.1.1”	Core functionality	0
“1.1.2”	Registry/Billing	0	should be zero (all closed in atlassian)...needs updating
1.1.1a	Core functionality	6	all testing time only. Maybe 60% of this testing could be done by non-dev team. Can also be done in parallel	6	parallel work can happen while we do other tasks?
1.1.1b	Stability and core features	11		17	09/09/12
1.1.1c	Stability and core features	16.675		33.675	20/09/12
1.1.1d	Data extraction module/functionality	40		73.675	20/10/12
“1.1.5”	Genotypic basic linking, storage and/or execution	50	mad guess...depends what is required	123.675	23/11/12	depends on trav & thilinas hours per week...the estimate its so crass given what is required is very undefined right now
1.1.1e	Getting prod env ready and transfering WAGER data/setting/ldap to prod	44	the more hands on deck testing: the less dev time for this.	167.675	06/01/13	this magical number allows for very little testing really...or for the inevitable bugs picked up in testing. The more help we get from now until the release day, the better to make sure peoples data is going to be as expected	Could sneak in before Xmas break, might sneak in after???

“1.1.5”	Genotypic basic linking, storage and/or execution	50	mad guess...depends what is required	217.675	12/02/13	depends on trav & thilinas hours per week...the estimate its so crass given what is required is very undefined right now
“1.1.6”	Enhanced data linkage and reporting	40	I wont even claim to have a decent guess at this...jsut throwing a number out there... what is this?	257.675	10/03/13	guesses are starting to get meaningless
“2.0.0”	feature requests and things like test scripts	56	this stuff may sneak up???	313.675	20/04/13
“3.0.0”	optomistic feature requests	16	this stuff may sneak up???	329.675	01/05/13
1.1.1b-admin	admin tasks not for developers	n\a	hopefully this is parallel to development	329.675	n/a
“1.1.4”	OLD Data extraction module/functionality project	ZERO...moved up above to make logical order		n/a