## 1.Header
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | GREEN
5.Changes | RED
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
Nectar Project Report
| 1. Header |  |  |  |  | OVERALL STATUS |  |  |  | RED
| Proj No. | RT029 |  | Proj. Name. | Cloud Based Bioinformatics Tools
| Report No. | 3 |  | Report Period From: | 30-Jun-12
|  |  |  | Report Period To: | 27-Jul-12
|  |  |  | Proj Manager: | Paul White
|  |  |  | Contracting Org: | University of Western Australia
STATUS FOR REPORTING PERIOD
| Complete the white boxes in each tab 2-9 noting that tabs 5 and 6 are as needed and tab 7 is when operational. The Status Lights will change in response to your data. Final signoff is on this tab. |  |  |  | 1.Header |  |  |  | LEGEND
[5 empty] | 2.Deliverables | GREEN
[5 empty] | 3.Issues | GREEN
[5 empty] | 4.Risks | GREEN
|  |  |  | As needed | 5.Changes | RED
|  |  |  | As needed | 6.Dependencies
|  |  |  | Once operational | 7.Measures
[5 empty] | 8.Communications | GREEN
[5 empty] | 9.Finance | RED | EIF | GREEN | Co-investment |  | RED
| See Legend |  |  |  | OVERALL STATUS | RED
[13 empty] | RED | AMBER | GREEN | OVERALL STATUS | RED
[13 empty] | 1 | 0 | 3
| Optional Comment | [10 empty] | Fin | 1 | 0 | 0
| Note that both Westmead Hospital and the Children's Cancer Institute of Australia have decided to move forward with The Ark for managing their biobanks. | [10 empty] | Total | 2 | 0 | 3
| Signoff | Yes | This is a true and fair representation of the state of the project for the reporting period. | [8 empty] | Checked?
TRUE
|  | Yes | We will seek the approval of NeCTAR for any changes to the agreed key personnel in this project.
TRUE
| Name of authorised officer: |  |  | Paul White | [7 empty] | 0
| Date: |  |  | 2012-08-15 11:07
Formulas:
Proj. Name. = IF(ISBLANK([Proj. Name., row above]),"",NOW())
Note on Q11: The University Of Melbourne: TO set up for a new project. 1. Proj No. Proj. Name Period From Period To Proj Manager Contracting Org 2. MILESTONES SHEET Add all deliverables (if multiple deliverable for a milestone, list each deliverable on a separate line. DELETE any blank rows. If more rows required, ensure you copy all formulas. LOCK SHEET 3. CHANGES If there is an open change, list it. 4. DEPENDENCIES Add all known external dependencies from table in proposal. See comment re modifying DEPENDENCYLIGHT. Hide col G. LOCK SHEET 5. MEASURES Add all known services and dates from table near 7.2 in proposal. LOCK SHEET 6. FINANCE Add finance data for THIS REPORTING PERIOD. Add planned cumulative totals (from report information sheet - will eventually be automatic) to T24,U24. LOCK SHEET 7. REPORT INFORMATION Complete report dates and planned finance. HIDE SHEET 7. ON HEADER SHEET, HIDE COL Q (THIS COMMENT) LOCK SHEET DONE

## 2.Milestones
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | GREEN
5.Changes | RED
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
| RT029 |  | Cloud Based Bioinformatics Tools
| From |  | 30-Jun-12
| To |  | 27-Jul-12
| Deliverables | [5 empty] | STATUS |  | GREEN
From proposal section 7.2
Scroll up for navigation | Milestone | Deliverable | Title | Deliverable | Target date of completion of milestone | % Complete | Actual Date of completion of milestone | Delay (No. Days Lag) | Funding Milestone? | Asset? | COMMENT and Remedial action for delayed milestones | Completion Status | STATUS
| 1 | 1 | Sub-contract signed (Linked to Funding Milestone 1) | Sub-contract | 2012-04-12 | 100 | 12-Apr-12 | 0 |  |  |  | COMPLETE
| 2 | 2 | Funding Milestone 1 | Linked to Milestone 1 | 2012-04-12 | 100 | 12-Apr-12 | 0 | y |  |  | COMPLETE
| 3 | 3 | Established Support Tools & Processes (Linked to Funding Milestone 2) | Support Tools & Processes | 2012-05-15 | 100 | 15-May-12 | 0 |  |  |  | COMPLETE
| 4 | 4 | Project Initiation complete (Linked to Funding Milestone 2) | Communications plan prepared and sent to NeCTAR (Signed contract + two months). | 2012-06-12 | 100 | 21-May-12 | -22 |  |  |  | COMPLETE
| 5 | 5 | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | Integrate existing application with AAF Authentication Services | 2012-06-14 | 100 | 14-Jun-12 | 0 |  | y | Functionality completed, system tested and deployed from Development to Test. Demonstration to Nik Zeps, Steering Committee member, scheduled for 14 June 2012 for signoff. | COMPLETE
| 6 | 6 | Funding Milestone 2 | Linked to Milestone 3, 4 and 5 | 2012-06-14 | 100 | 14-Jun-12 | 0 | y |  | Funding milestone completed | COMPLETE
| 7 | 7 | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | Integrated Invoicing & Billing Module | 2012-08-15 | 75 |  |  |  | y | 90% coding completed and tested. On target to be completed by 31st August - the revised date for Funding Milestone 3 - as per change request being handled by Sarah Mulvey. | Not Due
| 8 | 8 | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | Initial Production Research Cloud Deployment | 2012-08-15 | 50 |  |  |  | y | Some delay due to team member illness and reprioritisation of milestones to commence work on Data Extraction for Analysis module earlier. | Not Due
| 9 | 9 | Funding Milestone 3 | Linked to Milestone 7 and 8 | 2012-08-15 | 0 |  |  | y |  | Note that a change request has been completed to move this date out to the 31st of August. | Not Due
| 10 | 10 | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | Data Extraction for Analysis Module | 2012-09-30 | 25 |  |  |  | y | Work commenced early as we decided to address some technical challenges we recently identified. These technical issues have been resolved. | Not Due
| 11 | 11 | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | Pedigree Storage & Visualisation Module | 2012-10-15 | 0 |  |  |  | y |  | Not Due
| 12 | 12 | Funding Milestone 4 | Linked to Milestone 10 and 11 | 2012-11-15 | 0 |  |  | y |  |  | Not Due
| 13 | 13 | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | Enhanced Data Linkage & Reporting Module | 2012-12-15 | 0 |  |  |  | y |  | Not Due
| 14 | 14 | Implemented Registry Management Module (Linked to Funding Milestone 5) | Registry Management Module | 2012-12-15 | 0 |  |  |  | y |  | Not Due
| 15 | 15 | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 5) | Integrate Genotypic Data Management Capability | 2013-02-28 | 0 |  |  |  | y |  | Not Due
| 16 | 16 | Funding Milestone 5 | Linked to Milestone 13, 14 and 15 Note that all development should be completed by 30 Jan 2013 | 2013-02-28 | 0 |  |  | y |  |  | Not Due
| 17 | 17 | Final Admin Closure (Funding Milestone 6) | Post-implementation Review (PIR) conducted and sent to NeCTAR.Practical Completion Certificate accepted by NeCTAR. | 2013-09-30 | 0 |  |  | y |  |  | Not Due
| 18 | 18 | Operations to June 2014 | Service Levels met and reported to NeCTAR as defined. | 2014-06-30 | 0 | [5 empty] | Not Due
[8 empty] | Av lag |  |  |  | OVERALL | GREEN
-3.6667
See Legend

## 3.Issues
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | GREEN
5.Changes | RED
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
| RT029 | Cloud Based Bioinformatics Tools
| From | 30-Jun-12
| To | 27-Jul-12
| Issues |  |  | STATUS | GREEN
High impact issues only. Show closed issues for one report and then remove.
| ID from your issues log | Issue | Date opened | Expected date closed | Date closed | No. Days between open and closed | No. Days between expected close and close | Status
Scroll up for navigation
| No. | Av days b/n exp close and close | Total Open |  | Total Closed |  |  |  | GREEN
| 0 |  | 0 |  | 0
See Legend

## 4.Risks
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | GREEN
5.Changes | RED
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
| RT029 | Cloud Based Bioinformatics Tools
| From | 30-Jun-12
| To | 27-Jul-12
| Risks |  | STATUS | GREEN
Top five risks.
| ID from your risk log | Brief description of risk | Mitigation | Residual risk rating
Scroll up for navigation | Ark-628 | The impact of the reduced $ and delay of the GVL project on genomics storage is unknown | Commenced investigating alternatives for storing genomic data efficiently as part of our toolset. | Amber
| 1 | Availability of appropriately skilled development resources. | Second part time developer has been hired in Melbourne. | Green
| 2 | Ongoing availability of partner organisation resources. | Resourcing is not currently an issue. | Green
| 3 | Availability RDSI, AAF and the Research Cloud. | RDSI dependency not imminent. NSP is not as stable as we would like as it has been taken done at least twice whilst we have been using it for production instances. We have also not had any responses to our questions regarding backup frequency and restoration procedures for the NSP server instances we have built and for the NFS storage being used for backups. | Amber
| 4 | Completeness of configuration documentation for new studies | Pushing back on deployment dates to ensure clients have clearly documented their configuration requirements | Amber
| See Legend |  |  |  | GREEN

## 5.Changes
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | GREEN
5.Changes | RED
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
| RT029 |  | Cloud Based Bioinformatics Tools
| From |  | 30-Jun-12
| To |  | 27-Jul-12
| Changes | [5 empty] | STATUS | RED |  | Number of changes: |  | 0
| All open changes. Show closed changes for one report and then remove. | [8 empty] | Average days to approve:
[10 empty] | Number of open changes: |  | 1
| No. (in Nectar register) | Change Title | Time impact (+/- days) | Cost impact (+/- $) | Date requested | Status | Anticipated Close (+28days) | Date approved | No. of days to approve
Scroll up for navigation | N1009 | RT029 Milestone Changes | 0 | 0 | 24-May-12 | open | 2012-06-21 |  |  | DUE | RED
| Total |  |  |  |  | Total Open |  |  | Average |  | RED
| 0 |  |  |  |  | 1
See Legend
Formulas:
Anticipated Close (+28days) = IF([Date requested]>0,[Date requested]+28,"")

## 6.Dependencies
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | GREEN
5.Changes | RED
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
| RT029 | Cloud Based Bioinformatics Tools
| From | 30-Jun-12
| To | 27-Jul-12
External Dependencies
List of External Dependencies. Add new rows as required.
| External party | Capability required | Date required | Milestone dependent on that capability | Optional Comment | New dependency?
Scroll up for navigation | AAF | ARCS Access Service | 01-Apr-12 | Integrated exist | Integration Complete
| RDSI | Research Data Service Infrastructure | 01-Aug-12 | Integrated Genot
| The Research Cloud | Application and database hosting |  | Initial Producti | We already have access to National Server Program servers so this is not a critical requirement
| IVEC | HPC Infrastructure & Services | 01-Aug-12 | Integrated Genot | IVEC resource assigned to assist with implementation
| Genomics Virtual Laboratory Project | Interface Definitions | 01-Jul-12 | Integrated Genot | This project has a delayed start so we are investigating the option of building some of this functionality ourselves in more detail
See Legend
Note on G24: The University Of Melbourne: 1. Add known dependencies from table in the proposal. 2. Put in style "prepopulated" (Blue) 3. Ensure code in "new dependency" column (G) is there for all new dependency rows (not existing) 4. Modify dependencylight to 1st new dependency row (e.g if there are 3 known dependencies, put it on 4th row) 5. Hide Col G

## 7.Measures
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | GREEN
5.Changes | RED
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
Scroll up for navigation | RT029 | Cloud Based Bioinformatics Tools
| From | 30-Jun-12
| To | 27-Jul-12
Measures of uptake
From production infrastructure
[6 empty] | No. of registered users |  | Average frequency of use |  | Number of phenotypic data sets |  | Biospecimen Counts |  | Active Studies |  | Subject Counts
| Service No | Service | Expected Pilot Date | Expected Production Date | Milestone No | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period
| 1 | Established Support Tools & Processes (Linked to Funding Milestone 2) | 2012-05-15 | 2012-05-15 | 3 | 5 | 5 | Daily | Daily |  |  |  |  | 1 | 1 | >1000 | >1000
| 2 | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | 2012-06-15 | 2012-08-15 | 5
| 3 | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 7
| 4 | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 8
| 5 | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | 2012-09-30 | 2012-10-30 | 10
| 6 | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | 2012-10-15 | 2012-11-15 | 11
| 7 | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 13
| 8 | Implemented Registry Management Module (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 14
| 9 | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 5) | 2013-02-28 | 2013-03-30 | 15
Number of Service Levels in Exception
* Not all measures will be relevant for a particular asset. Only complete details for the appropriate measures.
See Legend
1. Registered Users – The number of users which have been registered to use the system. This can be extracted using a simple SQL query against each system instance.
2. Average Use Frequency – The average frequency of use for registered users. This can be extracted using a simple SQL query against each system instance. This query would be against the user authentication logs.
3. Phenotypic Datasets – The number of phenotypic/questionnaire/clinical datasets that have been created. This can be extracted using a simple SQL query against each system instance.
4. Biospecimen Counts – The total number of physical biospecimens under management by the system. This can be extracted using a simple SQL query against each system instance.
5. Active Studies – The number of active biobanks, research studies, cohorts, registries and trials for which the system is being used. This can be extracted using a simple SQL query against each system instance.
6. Subject Counts – The number of participants/subjects for which data is being managed across the different studies. This can be extracted using a simple SQL query against each system instance.

## 8.Communications
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | GREEN
5.Changes | RED
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
| RT029 | Cloud Based Bioinformatics Tools
| From | 30-Jun-12
| To | 27-Jul-12
| Communications |  |  | GREEN
| Activities this period | Type | Has Occurred? | URL | Activity
Scroll up for navigation | Email to candidate studies to trial new system | e-news | Yes |  | THIS PERIOD 1
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
| Activities upcoming | Type |  | URL
| Broadly distributed email showcasing production projects and the software capabilities | event |  |  | PLANNED 1
| See Legend |  |  |  | 1
1
GREEN

## 9.Finance
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | GREEN
5.Changes | RED
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
| RT029 | Cloud Based Bioinformatics Tools
| From | 30-Jun-12
| To | 27-Jul-12
| Finance |  |  |  |  | STATUS | RED
| Totals for this reporting period | [7 empty] | THIS REPORT
CUMULATIVE
[9 empty] | EIFdiff | EIF VALUE | Co-investDiff | Co-inv value | OVERALLFIN | % Diff EIF | % Diff Co
|  |  | Planned |  |  | Actual | [9 empty] | Planned Cumulative |  |  | Actual Cumulative |  |  | EIF Diff | EIF VALUE | Co DIFF | Co VALUE | OVERALL
|  |  | EIF | In-kind | Cash | EIF | In-kind | Cash | [7 empty] | EIF | Coinvestment | Total | EIF | Coinvestment | Total
Scroll up for navigation | Equipment |  | 0 | 0 | 0
| Personnel |  | 0 | 0 | 0
| Other |  | 0 | 0 | 0 |  | 16094
| Total |  | 0 | 0 | 0 | 0 | 16094 | 0 |  |  |  |  | GREEN |  |  | 104000 | 73000 | 177000 | 104000 | 39773 | 143773 | 0 | GREEN | -0.45516 | RED | RED
Outstanding Commitments (if relevant)
Optional Comment
See Legend

## Legend
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | GREEN
5.Changes | RED
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
LEGEND
|  |  | Green | Amber | Red
|  | 1. Header | Displays OVERALL Status
|  | 2.Deliverables | <2 days late | >1 <28 days late | >28 days late
|  | 3.Issues | <2 days late | >1 <28 days late | >28 days late
|  | 4.Risks | 5 identified | N/A | <5 identified
|  | 5.Changes | <2 days late | >1 <28 days late | >28 days late
|  | 6.Dependencies | N/A | N/A | N/A
|  | 7.Measures | N/A | N/A | N/A
|  | 8.Communications | >0 activity in each period | <1 activity planned | <1 activity this period
|  | 9.Finance | <10% over or underspend (total) | >10% <20% under or overspend (total) | >20% under or overspend (total)
|  | OVERALL STATUS | 0 sections RED (excluding comms) AND < 2 sections AMBER (excluding comms) AND Finance=GREEN AND Deliverables=GREEN | >2 sections (except comms) amber; OR Finance or deliverables are AMBER; AND 0 sections (except comms) red | >0 sections (except comms) red

## Data- TO BE HIDDEN (hidden)
Status | Percentage | CommsType | RiskRating | YesNo | EarliestDate | LatestDate | StatusItems | AssetType
open | 0 | e-news | Green | Yes | 2012-01-01 | 2014-06-30 | Pilot | Hardware
closed | 25 | press release | Amber | No |  |  | Production | Software
| 50 | radio item | Red |  |  |  | Out of Service | Document
| 75 | television item | [5 empty] | Other
| 100 | article
event
social media

## ReportInformation (hidden)
Report No. | Funding? | Report | Start Date | Report Date | Due By | Planned EIF Spend Equipment | Planned EIF Spend Personnel | Planned EIF Spend Other | Planned In-kind Spend Equipment | Planned In-kind Spend Personnel | Planned In-kind Spend Other | Planned Coinvestment Cash Spend Equipment | Planned Coinvestment Cash Spend Personnel | Planned Coinvestment Cash Spend Other | Planned Total EIF | Planned Total Co | Planned cumulative EIF | Planned cumulative co | Planned cumulative total | Actual EIF | Actual Co | Actual Cumulative EIF | Actual Cumulative Coinvestment | Actual Cumulative Total
1 |  |  | 2012-04-12 | 2012-06-01 | 2012-06-15 |  | 52000 |  |  |  | 24000 |  |  |  | 52000 | 24000 | 52000 | 24000 | 76000 | 52000 | 1000 | 52000 | 1000 | 53000
2 |  |  |  | 2012-06-29 | 2012-07-13 |  | 52000 |  |  |  | 49000 |  |  |  | 52000 | 49000 | 104000 | 73000 | 177000 | 52000 | 22679 | 104000 | 23679 | 127679
3 |  |  |  | 2012-07-27 | 2012-08-10 | [9 empty] | 0 | 0 | 104000 | 73000 | 177000 |  |  | 104000 | 23679 | 127679
4 |  |  |  | 2012-08-31 | 2012-09-14 |  | 52000 |  |  |  | 14000 |  |  |  | 52000 | 14000 | 156000 | 87000 | 243000 |  |  | 104000 | 23679 | 127679
5 |  |  |  | 2012-11-30 | 2012-12-14 |  | 52000 |  |  |  | 48000 |  |  |  | 52000 | 48000 | 208000 | 135000 | 343000 |  |  | 104000 | 23679 | 127679
6 |  |  |  | 2013-03-01 | 2013-03-15 |  | 52000 | [7 empty] | 52000 | 0 | 260000 | 135000 | 395000 |  |  | 104000 | 23679 | 127679
7 |  |  |  | 2013-05-24 | 2013-06-07 | [9 empty] | 0 | 0 | 260000 | 135000 | 395000 |  |  | 104000 | 23679 | 127679
8 |  |  |  | 2013-08-23 | 2013-09-06 | [9 empty] | 0 | 0 | 260000 | 135000 | 395000 |  |  | 104000 | 23679 | 127679
9 |  |  |  | 2013-11-22 | 2013-12-06 |  | 29000 | [7 empty] | 29000 | 0 | 289000 | 135000 | 424000 |  |  | 104000 | 23679 | 127679
[19 empty] | Total |  |  | 104000 | 23679 | 127679
Note on U2: The University Of Melbourne: These fields are to come from the database. On creating report 2, report 1 data will be included in the actual EIF and Actual Co row against report 1.

## 10.Assets
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | GREEN
5.Changes | RED
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
| RT029 | Cloud Based Bioinformatics Tools
| From | 30-Jun-12
| To | 27-Jul-12
Assets
Complete a row in the table below for any assets delivered
Select a cell for further information.
| Ref | Asset Type | Name | Version Number | Owner/ Custodian | Value | Location | Local Asset Tag | Status
|  | Software | AAF Integration | 1.1.1 | UWA | 24164 | Atlassian Subversion Repository