## 1.Header
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | RED
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
Nectar Project Report
| 1. Header |  |  |  | OVERALL STATUS |  |  |  | RED
| Proj No. | RT029 | Proj. Name. | Cloud Based Bioinformatics Tools
| Report No. | 1 | Report Period From: | 2012-04-12
|  |  | Report Period To: | 2012-06-01
|  |  | Date Submitted: | 2012-06-13
|  |  | Proj Manager: | Paul White
|  |  | Contracting Org: | University of Western Australia
STATUS FOR REPORTING PERIOD
| Complete the white boxes in each tab 2-9 noting that tabs 5 and 6 are as needed and tab 7 is when operational. The Status Lights will change in response to your data. Final signoff is on this tab. |  |  | 1.Header | RED |  |  | LEGEND
|  |  |  | 2.Deliverables | GREEN
|  |  |  | 3.Issues | GREEN
|  |  |  | 4.Risks | RED
|  |  | As needed | 5.Changes | GREEN
|  |  | As needed | 6.Dependencies
|  |  | Once operational | 7.Measures
|  |  |  | 8.Communications | GREEN
|  |  |  | 9.Finance | RED | EIF | GREEN | Co-investment |  | RED
| See Legend |  |  | OVERALL STATUS | RED
[12 empty] | RED | AMBER | GREEN | OVERALL STATUS | RED
[12 empty] | 1 | 0 | 3
| Optional Comment | [9 empty] | Fin | 1 | 0 | 0
[11 empty] | Total | 2 | 0 | 3
| Signoff | [9 empty] | Checked?
TRUE
TRUE
| Name of authorised officer: |  | Paul White | [7 empty] | 0
| Date: |  | 2012-06-13 17:50
Formulas:
Proj. Name. = IF(ISBLANK([Proj. Name., row above]),"",NOW())

## 2.Milestones
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | RED
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
| RT029 |  | Cloud Based Bioinformatics Tools
| From |  | 2012-04-12
| To |  | 2012-06-01
| Deliverables | [5 empty] | STATUS |  | GREEN
From proposal section 7.2
Scroll up for navigation | Milestone | Deliverable | Title | Deliverable | Target date of completion of milestone | % Complete | Actual Date of completion of milestone | Delay (No. Days Lag) | Funding Milestone? | Asset? | COMMENT and Remedial action for delayed milestones | Completion Status | STATUS
| 1 | 1 | Sub-contract signed (Linked to Funding Milestone 1) | Sub-contract | 2012-04-12 | 100 | 2012-04-12 | 0 |  |  |  | COMPLETE |  | 2012-04-12
| 2 | 2 | Funding Milestone 1 | Linked to Milestone 1 | 2012-04-12 | 100 | 2012-04-12 | 0 | y |  |  | COMPLETE
| 3 | 3 | Established Support Tools & Processes (Linked to Funding Milestone 2) | Support Tools & Processes | 2012-05-15 | 100 | 2012-05-15 | 0 |  |  |  | COMPLETE
| 4 | 4 | Project Initiation complete (Linked to Funding Milestone 2) | Communications plan prepared and sent to NeCTAR (Signed contract + two months). | 2012-06-12 | 100 | 2012-05-21 | -22 |  |  |  | Not Due
| 5 | 5 | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | Integrate existing application with AAF Authentication Services | 2012-06-14 | 75 |  |  |  | y | Functionality completed, system tested and deployed from Development to Test. Demonstration to Nik Zeps, Steering Committee member, scheduled for 14 June 2012 for signoff. | Not Due
| 6 | 6 | Funding Milestone 2 | Linked to Milestone 3, 4 and 5 | 2012-06-14 | 0 |  |  | y |  |  | Not Due
| 7 | 7 | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | Integrated Invoicing & Billing Module | 2012-08-15 | 0 |  |  |  | y |  | Not Due
| 8 | 8 | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | Initial Production Research Cloud Deployment | 2012-08-15 | 0 |  |  |  | y |  | Not Due
| 9 | 9 | Funding Milestone 3 | Linked to Milestone 7 and 8 | 2012-08-15 | 0 |  |  | y |  |  | Not Due
| 10 | 10 | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | Data Extraction for Analysis Module | 2012-09-30 | 0 |  |  |  | y |  | Not Due
| 11 | 11 | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | Pedigree Storage & Visualisation Module | 2012-10-15 | 0 |  |  |  | y |  | Not Due
| 12 | 12 | Funding Milestone 4 | Linked to Milestone 10 and 11 | 2012-11-15 | 0 |  |  | y |  |  | Not Due
| 13 | 13 | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | Enhanced Data Linkage & Reporting Module | 2012-12-15 | 0 |  |  |  | y |  | Not Due
| 14 | 14 | Implemented Registry Management Module (Linked to Funding Milestone 5) | Registry Management Module | 2012-12-15 | 0 |  |  |  | y |  | Not Due
| 15 | 15 | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 5) | Integrate Genotypic Data Management Capability | 2013-02-28 | 0 |  |  |  | y |  | Not Due
| 16 | 16 | Funding Milestone 5 | Linked to Milestone 13, 14 and 15 Note that all development should be completed by 30 Jan 2013 | 2013-02-28 | 0 |  |  | y |  |  | Not Due
| 17 | 17 | Final Admin Closure (Funding Milestone 6) | Post-implementation Review (PIR) conducted and sent to NeCTAR.Practical Completion Certificate accepted by NeCTAR. | 2013-09-30 | 0 |  |  | y |  |  | Not Due
| 18 | 18 | Operations to June 2014 | Service Levels met and reported to NeCTAR as defined. | 2014-06-30 | 0 | [5 empty] | Not Due
[8 empty] | Av lag |  |  |  | OVERALL | GREEN
-5.5
See Legend

## 3.Issues
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | RED
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
| RT029 | Cloud Based Bioinformatics Tools
| From | 2012-04-12
| To | 2012-06-01
| Issues |  |  | STATUS | GREEN
High impact issues only. Show closed issues for one report and then remove.
| ID from your issues log | Issue | Date opened | Expected date closed | Date closed | No. Days between open and closed | No. Days between expected close and close | Status
Scroll up for navigation
| No. | Av days b/n exp close and close | Total Open |  | Total Closed |  |  |  | GREEN
| 0 |  | 0 |  | 0
See Legend

## 4.Risks
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | RED
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
| RT029 | Cloud Based Bioinformatics Tools
| From | 2012-04-12
| To | 2012-06-01
| Risks |  | STATUS | RED
Top five risks.
| ID from your risk log | Brief description of risk | Mitigation | Residual risk rating
Scroll up for navigation | Ark-628 | The impact of the reduced $ and delay of the GVL project on genomics storage is unknown | Commenced investigating alternatives for storing genomic data efficiently as part of our toolset. | Amber
| 1 | Availability of appropriately skilled development resources. | Second part time developer has been hired in Melbourne. | Green
| 2 | Ongoing availability of partner organisation resources. | Resourcing is not currently an issue. | Green
| 3 | Availability RDSI, AAF and the Research Cloud. | Utilising NSP until RC can offer backup facilities. AAF progressing well, RDSI dependency not imminent. | Green
ENTER RISK 5
| See Legend |  |  |  | RED

## 5.Changes
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | RED
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
| RT029 |  | Cloud Based Bioinformatics Tools
| From |  | 2012-04-12
| To |  | 2012-06-01
| Changes | [5 empty] | STATUS | GREEN |  | Number of changes: |  | 0
| All open changes. Show closed changes for one report and then remove. | [8 empty] | Average days to approve:
[10 empty] | Number of open changes: |  | 1
| No. (in Nectar register) | Change Title | Time impact (+/- days) | Cost impact (+/- $) | Date requested | Status | Anticipated Close (+28days) | Date approved | No. of days to approve
Scroll up for navigation | N1009 | RT029 Milestone Changes |  |  | 2012-05-24 | open | 2012-06-21 |  |  | NOT DUE
| Total |  |  |  |  | Total Open |  |  | Average |  | GREEN
| 0 |  |  |  |  | 1
See Legend
Formulas:
Anticipated Close (+28days) = IF([Date requested]>0,[Date requested]+28,"")

## 6.Dependencies
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | RED
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
| RT029 | Cloud Based Bioinformatics Tools
| From | 2012-04-12
| To | 2012-06-01
External Dependencies
List of External Dependencies. As new rows as required.
| External party | Capability required | Date required | Milestone dependent on that capability | Optional Comment | New dependency?
Scroll up for navigation | AAF | ARCS Access Service | 2012-04-01 | Integrated existing application with AAF Authentication Services | Integration Complete
| RDSI | Research Data Service Infrastructure | 2012-08-01 | Integrated Genotypic Data Management Capability
| The Research Cloud | Application and database hosting |  | Initial Production Research Cloud Deployment | We already have access to National Server Program servers so this is not a critical requirement
| IVEC | HPC Infrastructure & Services | 2012-08-01 | Integrated Genotypic Data Management Capability
| Genomics Virtual Laboratory Project | Interface Definitions | 2012-07-01 | Integrated Genotypic Data Management Capability | This project has a delayed start so we are investigating the option of building some of this functionality ourselves in more detail
See Legend

## 7.Measures
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | RED
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
Scroll up for navigation | RT029 | Cloud Based Bioinformatics Tools
| From | 2012-04-12
| To | 2012-06-01
Measures of uptake
From production infrastructure
[6 empty] | No. of registered users * |  | Average frequency of use * |  | Number of data sets uploaded * |  | Measure 4 (To be agreed) |  | Measure 5 (To be agreed) |  | Measure 6 (To be agreed)
| Service No | Service | Expected Pilot Date | Expected Production Date | Milestone No | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period
| 1 | Established Support Tools & Processes (Linked to Funding Milestone 2) | 2012-05-15 | 2012-05-15 | 3 |  | 5 |  | Daily
| 2 | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | 2012-06-15 | 2012-08-15 | 5
| 3 | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 7
| 4 | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 8
| 5 | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | 2012-09-30 | 2012-10-30 | 10
| 6 | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | 2012-10-15 | 2012-11-15 | 11
| 7 | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 13
| 8 | Implemented Registry Management Module (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 14
| 9 | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 5) | 2013-02-28 | 2013-03-30 | 15
Number of Service Levels in Exception
* Not all measures will be relevant for a particular asset. Only complete details for the appropriate measures.
See Legend

## 8.Communications
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | RED
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
| RT029 | Cloud Based Bioinformatics Tools
| From | 2012-04-12
| To | 2012-06-01
| Communications |  |  | GREEN
| Activities this period | Type | Has Occurred? | URL | Activity
Scroll up for navigation | NeCTAR project signing announcement, Project Launch | e-news | Yes | http://nectar.org.au/news/nectar-signs-first-e-research-tool-contract-uwa | THIS PERIOD 1
| Presentations to Westmead Hospital and CCIA | event | Yes |  | THIS PERIOD 1
| Updated The-Ark.org.au website | article | Yes | www.the-ark.org.au | THIS PERIOD 1
| Conduct 1st Steering Committee Meeting | event | Yes |  | THIS PERIOD 1
| Activities upcoming | Type |  | URL
| Drafted UWA press release (Nik Zeps) | press release |  |  | PLANNED 1
| Update OBiBa website | article |  |  | PLANNED 1
| See Legend |  |  |  | 4
2
GREEN

## 9.Finance
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | RED
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
| RT029 | Cloud Based Bioinformatics Tools
| From | 2012-04-12
| To | 2012-06-01
| Finance |  |  |  |  | STATUS | RED
Totals for this reporting period
[9 empty] | EIFdiff | EIF VALUE | Co-investDiff | Co-inv value | OVERALLFIN | % Diff EIF | % Diff Co
|  |  | Planned |  |  | Actual
|  |  | EIF | In-kind | Cash | EIF | In-kind | Cash
Scroll up for navigation | Equipment
| Personnel |  | 52000 | 1000 |  | 52000 | 1000
| Other |  |  |  | 20000 |  |  | 0
| Total |  | 52000 | 1000 | 20000 | 52000 | 1000 | 0 | 0 | GREEN | -0.95238 | RED | RED | 0 | -95.2381
Optional Comment
Cash component to be contributed for travel - awaiting completion of the funds transfer from UWA Matching Research funds account. Centre funds to be transferred when UWA funds received. Funds expected imminently.
See Legend

## Legend
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | RED
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
LEGEND
|  |  | Green | Amber | Red
|  | 1. Header | Displays OVERALL Status
|  | 2.Deliverables | <2 days late | >1 <28 days late | >28 days late
|  | 3.Issues | <2 days late | >1 <28 days late | >28 days late
|  | 4.Risks | 5 identified | N/A | <5 identified
|  | 5.Changes | <2 days late | >1 <28 days late | >28 days late
|  | 6.Dependencies | N/A | N/A | N/A
|  | 7.Measures | N/A | N/A | N/A
|  | 8.Communications | >0 activity in each period | <1 activity planned | <1 activity this period
|  | 9.Finance | <10% over or underspend (total) | >10% <20% under or overspend (total) | >20% under or overspend (total)
|  | OVERALL STATUS | 0 sections RED (excluding comms) AND < 2 sections AMBER (excluding comms) AND Finance=GREEN AND Deliverables=GREEN | >2 sections (except comms) amber; OR Finance or deliverables are AMBER; AND 0 sections (except comms) red | >0 sections (except comms) red

## Data- TO BE HIDDEN
Status | Percentage | CommsType | RiskRating | YesNo
open | 0 | e-news | Green | Yes
closed | 25 | press release | Amber | No
| 50 | radio item | Red
| 75 | television item
| 100 | article
event
social media