## 1.Header
1.Header | AMBER
2.Deliverables | RED
3.Issues | GREEN
4.Risks | GREEN
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | AMBER
9.Finance | GREEN
Nectar Project Report
| 1. Header |  |  |  |  | OVERALL STATUS |  | AMBER
| Proj No. | RT029 |  | Proj. Name. | Cloud Based Bioinformatics Tools
| Report No. | 6 |  | Report Period From: | 2012-12-01
|  |  |  | Report Period To: | 2013-03-01
|  |  |  | Proj Manager: | Paul White
|  |  |  | Contracting Org: | University of Western Australia
STATUS FOR REPORTING PERIOD
| Complete the white boxes in each tab 2-9 noting that tabs 5 and 6 are as needed and tab 7 is when operational. The Status Lights will change in response to your data. Final signoff is on this tab. |  |  |  | 1.Header |  | LEGEND
[5 empty] | 2.Deliverables | RED
[5 empty] | 3.Issues | GREEN
[5 empty] | 4.Risks | GREEN
|  |  |  | As needed | 5.Changes | GREEN
|  |  |  | As needed | 6.Dependencies
|  |  |  | Once operational | 7.Measures
[5 empty] | 8.Communications | AMBER
[5 empty] | 9.Finance | GREEN
| See Legend |  |  |  | OVERALL STATUS | AMBER
[10 empty] | RED | AMBER | GREEN | OVERALL STATUS | AMBER
[10 empty] | 1 | 0 | 2
| Optional Comment | [7 empty] | Fin | 0 | 0 | 1
[9 empty] | Total | 1 | 0 | 3
| Signoff |  | This is a true and fair representation of the state of the project for the reporting period. | [5 empty] | Checked?
FALSE
We will seek the approval of NeCTAR for any changes to the agreed key personnel in this project.
FALSE
| Name of authorised officer: | [7 empty] | 0
Date:
Please signoff (select Yes and enter name) prior to form submission
Note on Q11: The University Of Melbourne: TO set up for a new project. 1. Proj No. Proj. Name Period From Period To Proj Manager Contracting Org 2. MILESTONES SHEET Add all deliverables (if multiple deliverable for a milestone, list each deliverable on a separate line. DELETE any blank rows. If more rows required, ensure you copy all formulas. LOCK SHEET 3. CHANGES If there is an open change, list it. 4. DEPENDENCIES Add all known external dependencies from table in proposal. See comment re modifying DEPENDENCYLIGHT. Hide col G. LOCK SHEET 5. MEASURES Add all known services and dates from table near 7.2 in proposal. LOCK SHEET 6. FINANCE Add finance data for THIS REPORTING PERIOD. Add planned cumulative totals (from report information sheet - will eventually be automatic) to T24,U24. LOCK SHEET FINANCE 2 CHECK FINANCE 2 Sheet for instructions. 7. REPORT INFORMATION Complete report dates and planned finance. HIDE SHEET 8. ON HEADER SHEET, HIDE COL Q (THIS COMMENT) LOCK SHEET DONE

## 2.Milestones
1.Header | AMBER
2.Deliverables | RED
3.Issues | GREEN
4.Risks | GREEN
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | AMBER
9.Finance | GREEN
| RT029 |  | Cloud Based Bioinformatics Tools
| From |  | 2012-12-01
| To |  | 2013-03-01
| Deliverables | [5 empty] | STATUS |  | RED
| From proposal section 7.2 |  |  | Updated with RFC N1009
Scroll up for navigation | Milestone | Deliverable | Title | Deliverable | Target date of completion of milestone | % Complete | Actual Date of completion of milestone | Delay (No. Days Lag) | Funding Milestone? | Asset? | COMMENT and Remedial action for delayed milestones |  | Completion Status | STATUS
| 1 | 1 | Sub-contract signed (Linked to Funding Milestone 1) | Sub-contract | 2012-04-12 | 100 | [5 empty] | COMMENT REQUIRED | NOT COMPLETE | RED
| 2 | 2 | Funding Milestone 1 | Linked to Milestone 1 | 2012-04-12 | 100 |  |  | y |  |  | COMMENT REQUIRED | NOT COMPLETE | RED
| 3 | 3 | Established Support Tools & Processes (Linked to Funding Milestone 2) | Support Tools & Processes | 2012-05-15 | 100 | [5 empty] | COMMENT REQUIRED | NOT COMPLETE | RED
| 4 | 4 | Project Initiation complete (Linked to Funding Milestone 2) | Communications plan prepared and sent to NeCTAR (Signed contract + two months). | 2012-07-01 | 100 | [5 empty] | COMMENT REQUIRED | NOT COMPLETE | RED
| 5 | 5 | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | Integrate existing application with AAF Authentication Services | 2012-06-14 | 100 |  |  |  | y | Functionality completed, system tested and deployed from Development to Test. Demonstration to Nik Zeps, Steering Committee member, scheduled for 14 June 2012 for signoff. | COMMENT REQUIRED | NOT COMPLETE | RED
| 6 | 6 | Funding Milestone 2 | Linked to Milestone 3, 4 and 5 | 2012-06-29 | 100 |  |  | y |  | Funding milestone completed | COMMENT REQUIRED | NOT COMPLETE | RED
| 7 | 7 | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | Integrated Invoicing & Billing Module | 2012-08-15 | 100 |  |  |  | y | Completed Coding and Testing - will submit for final Steering Committee signoff along with initial Production Research Cloud Deployment for Funding Milestone 3 | COMMENT REQUIRED | NOT COMPLETE | RED
| 8 | 8 | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | Initial Production Research Cloud Deployment | 2012-08-15 | 100 | Enter date of completion |  |  | y | Some delay due to team member illness and reprioritisation of milestones to commence work on Data Extraction for Analysis module earlier. ADDITIONAL COMMENT |  | COMPLETE
| 9 | 9 | Funding Milestone 3 | Linked to Milestone 7 and 8 | 2012-08-31 | 100 | Enter date of completion |  | y |  | Note that a change request has been completed to move this date out to the 31st of August. |  | COMPLETE
| 10 | 10 | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | Data Extraction for Analysis Module | 2012-09-30 | 75 |  |  |  | y | Work is approximately 60% complete and on track for completion of first release in December 2012. | COMMENT REQUIRED | NOT COMPLETE | RED
| 11 | 11 | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | Pedigree Storage & Visualisation Module | 2012-10-15 | 25 |  |  |  | y | Have completed design work and database schema changes. Have also identified suitable pedigree visualisation tool for integration. | COMMENT REQUIRED | NOT COMPLETE | RED
| 12 | 12 | Funding Milestone 4 | Linked to Milestone 10 and 11 | 2012-11-30 | 50 |  |  | y |  | Approx 40% complete as Data Extraction is the majority of this milestone. | COMMENT REQUIRED | NOT COMPLETE | RED
| 13 | 13 | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | Enhanced Data Linkage & Reporting Module | 2012-12-15 | 50 |  |  |  | y | Have completed a number of the required reporting enhancements ADDITIONAL COMMENT | COMMENT REQUIRED | NOT COMPLETE | RED
| 14 | 14 | Implemented Registry Management Module (Linked to Funding Milestone 5) | Registry Management Module | 2012-12-15 | 100 | Enter date of completion |  |  | y | Implemented and tested sub-study management capability to allow subjects from a parent study to be allocated to sub-studies without duplicating core subject data |  | COMPLETE
| 15 | 15 | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 5) | Integrate Genotypic Data Management Capability | 2013-02-28 | 0 |  |  |  | y |  | COMMENT REQUIRED | NOT COMPLETE | GREEN
| 16 | 16 | Funding Milestone 5 | Linked to Milestone 13, 14 and 15 Note that all development should be completed by 30 Jan 2013 | 2013-03-01 | 0 |  |  | y |  |  | COMMENT REQUIRED | NOT COMPLETE | GREEN
| 17 | 17 | Final Admin Closure (Funding Milestone 6) | Post-implementation Review (PIR) conducted and sent to NeCTAR.Practical Completion Certificate accepted by NeCTAR. | 2013-11-22 | 0 |  |  | y |  |  |  | Not Due
| 18 | 18 | Operations to June 2014 | Service Levels met and reported to NeCTAR as defined. | 2014-06-30 | 0 | [6 empty] | Not Due
[8 empty] | Av lag |  |  |  |  | OVERALL | RED
See Legend

## 3.Issues
1.Header | AMBER
2.Deliverables | RED
3.Issues | GREEN
4.Risks | GREEN
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | AMBER
9.Finance | GREEN
| RT029 | Cloud Based Bioinformatics Tools
| From | 2012-12-01
| To | 2013-03-01
| Issues |  |  | STATUS | GREEN
High impact issues only. Closed issues will be removed automatically for the next report template.
| ID from your issues log *Required Field | Issue | Date opened | Expected date closed | Date closed | No. Days between open and closed | No. Days between expected close and close | Status
Scroll up for navigation | [8 empty] | GREEN
GREEN
GREEN
GREEN
GREEN
GREEN
GREEN
GREEN
| No. | Av days b/n exp close and close | Total Open |  | Total Closed |  |  |  | GREEN
| 0 |  | 0 |  | 0
See Legend

## 4.Risks
1.Header | AMBER
2.Deliverables | RED
3.Issues | GREEN
4.Risks | GREEN
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | AMBER
9.Finance | GREEN
| RT029 | Cloud Based Bioinformatics Tools
| From | 2012-12-01
| To | 2013-03-01
| Risks |  | STATUS | GREEN
Top five risks. Once a risk has occurred, please move it to an Issue and replace with another risk.
| ID from your risk log * Required Field | Brief description of risk | Mitigation | Residual risk rating
Scroll up for navigation | Ark-628 | The impact of the reduced $ and delay of the GVL project on genomics storage is unknown | Genomic Data Repository (installed at UNSW) determined not to be suitable so will be developing a solution in-house. | Amber
| 1 | Availability of appropriately skilled development resources. | One developer has been ill and may need extended sick leave. Have submitted a n RFC to adjust milestone dates and have identified another part time develop to assist. | Amber
| 2 | Ongoing availability of partner organisation resources. | Resourcing is not currently an issue. | Green
| 3 | Availability RDSI, AAF and the Research Cloud. | NSP stability is good. UWA will support use of UWA AAF services for production authentication. | Green
| 4 | Completeness of configuration documentation for new studies | Pushing back on deployment dates to ensure clients have clearly documented their configuration requirements | Amber
| See Legend |  |  |  | GREEN

## 5.Changes
1.Header | AMBER
2.Deliverables | RED
3.Issues | GREEN
4.Risks | GREEN
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | AMBER
9.Finance | GREEN
| RT029 |  | Cloud Based Bioinformatics Tools
| From |  | 2012-12-01
| To |  | 2013-03-01
| Changes | [5 empty] | STATUS | GREEN |  | Number of changes: |  | 0
| All changes formally requested through a Request For Change (RFC). | [8 empty] | Average days to approve: |  | 99
[10 empty] | Number of open changes: |  | 0
| No. (in Nectar register) * Req'd Field | Change Title | Time impact (+/- days) | Cost impact (+/- $) | Date requested | Status | Anticipated Close (+28days) | Date approved | No. of days to approve
Scroll up for navigation | N1009 | RT029 Milestone Changes | 0 | 0 | 2012-05-24 | closed | 2012-06-21 | 2012-08-31 | 99
| Total |  |  |  |  | Total Open |  |  | Average |  | GREEN
| 0 |  |  |  |  | 0 |  |  | 99
See Legend
Formulas:
Anticipated Close (+28days) = IF([Date requested]>0,[Date requested]+28,"")

## 6.Dependencies
1.Header | AMBER
2.Deliverables | RED
3.Issues | GREEN
4.Risks | GREEN
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | AMBER
9.Finance | GREEN
| RT029 | Cloud Based Bioinformatics Tools
| From | 2012-12-01
| To | 2013-03-01
External Dependencies
List of External Dependencies. Add new rows as required.
| External party | Capability required | Date required | Milestone dependent on that capability | Optional Comment | New dependency?
Scroll up for navigation | AAF | ARCS Access Service | 2012-04-01 | Integrated exist | Have received UWA permission to use one of the Universities service allocation of 12 services for use in production
| RDSI | Research Data Service Infrastructure | 2012-08-01 | Integrated Genot
| The Research Cloud | Application and database hosting |  | Initial Producti | We already have access to National Server Program servers so this is not a critical requirement
| IVEC | HPC Infrastructure & Services | 2012-08-01 | Integrated Genot | IVEC resource assigned to assist with implementation
| Genomics Virtual Laboratory Project | Interface Definitions | 2012-07-01 | Integrated Genot | This project has now been signed off by NeCTAR so we are moving forward to determine solution fit.
See Legend
Note on G24: The University Of Melbourne: 1. Add known dependencies from table in the proposal. 2. Put in style "prepopulated" (Blue) 3. Ensure code in "new dependency" column (G) is there for all new dependency rows (not existing) 4. Modify dependencylight to 1st new dependency row (e.g if there are 3 known dependencies, put it on 4th row) 5. Hide Col G

## 7.Measures
1.Header | AMBER
2.Deliverables | RED
3.Issues | GREEN
4.Risks | GREEN
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | AMBER
9.Finance | GREEN
Scroll up for navigation | RT029 | Cloud Based Bioinformatics Tools
| From | 2012-12-01
| To | 2013-03-01
Measures of uptake
From production infrastructure
[6 empty] | No. of registered users |  | Average frequency of use |  | Number of phenotypic data sets |  | Biospecimen Counts |  | Active Studies |  | Subject Counts
| Service No | Service | Expected Pilot Date | Expected Production Date | Milestone No | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period
| 1 | Established Support Tools & Processes (Linked to Funding Milestone 2) | 2012-05-15 | 2012-05-15 | 3 | 5 |  | Daily | [6 empty] | 1 | 25000 | ??
| 2 | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | 2012-06-15 | 2012-08-15 | 5 |  | 5 |  | Daily
| 3 | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 7 |  | 5 |  | Daily
| 4 | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 8 |  | 5 |  | Daily |  |  |  | ??
| 5 | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | 2012-09-30 | 2012-10-30 | 10
| 6 | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | 2012-10-15 | 2012-11-15 | 11
| 7 | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 13
| 8 | Implemented Registry Management Module (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 14 |  | 5 |  | Daily
| 9 | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 5) | 2013-02-28 | 2013-03-30 | 15
Number of Service Levels in Exception
* Not all measures will be relevant for a particular asset. Only complete details for the appropriate measures.
See Legend
1. Registered Users – The number of users which have been registered to use the system. This can be extracted using a simple SQL query against each system instance.
2. Average Use Frequency – The average frequency of use for registered users. This can be extracted using a simple SQL query against each system instance. This query would be against the user authentication logs.
3. Phenotypic Datasets – The number of phenotypic/questionnaire/clinical datasets that have been created. This can be extracted using a simple SQL query against each system instance.
4. Biospecimen Counts – The total number of physical biospecimens under management by the system. This can be extracted using a simple SQL query against each system instance.
5. Active Studies – The number of active biobanks, research studies, cohorts, registries and trials for which the system is being used. This can be extracted using a simple SQL query against each system instance.
6. Subject Counts – The number of participants/subjects for which data is being managed across the different studies. This can be extracted using a simple SQL query against each system instance.

## 8.Communications
1.Header | AMBER
2.Deliverables | RED
3.Issues | GREEN
4.Risks | GREEN
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | AMBER
9.Finance | GREEN
| RT029 | Cloud Based Bioinformatics Tools
| From | 2012-12-01
| To | 2013-03-01
| Communications |  |  | AMBER
| Activities this period | Type | Has Occurred? | URL | Activity
Scroll up for navigation | Broadly distributed email showcasing production projects and the software capabilities | event | No |  | THIS PERIOD 1
| Second Steering Committee meeting | event | Yes |  | THIS PERIOD 1
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
| Activities upcoming | Type |  | URL
| See Legend |  |  |  | 2
0
AMBER

## 9.Finance (hidden)
1.Header | AMBER
2.Deliverables | RED
3.Issues | GREEN
4.Risks | GREEN
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | AMBER
9.Finance | GREEN
| RT029 | Cloud Based Bioinformatics Tools
| From | 2012-12-01
| To | 2013-03-01
| Finance |  |  |  |  | STATUS | GREEN
| Totals for this reporting period | [7 empty] | THIS REPORT
CUMULATIVE
[9 empty] | EIFdiff | EIF VALUE | Co-investDiff | Co-inv value | OVERALLFIN | % Diff EIF | % Diff Co
|  |  | Planned |  |  | Actual | [9 empty] | Planned Cumulative |  |  | Actual Cumulative |  |  | EIF Diff | EIF VALUE | Co DIFF | Co VALUE | OVERALL
|  |  | EIF | In-kind | Cash | EIF | In-kind | Cash | [7 empty] | EIF | Coinvestment | Total | EIF | Coinvestment | Total
Scroll up for navigation | Equipment |  | 0 | 0 | 0
| Personnel |  | 52000 | 0 | 0
| Other |  | 0 | 0 | 0
| Total |  | 52000 | 0 | 0 | 0 | 0 | 0 | -1 | RED |  |  | RED | -100 |  | 260000 | 135000 | 395000 | 169000 | 114000 | 283000 | -0.35 | RED | -0.15556 | AMBER | RED
Outstanding Commitments (if relevant)
Optional Comment
See Legend

## Legend
1.Header | AMBER
2.Deliverables | RED
3.Issues | GREEN
4.Risks | GREEN
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | AMBER
9.Finance | GREEN
LEGEND
|  |  | Green | Amber | Red
|  | 1. Header | Displays OVERALL Status
|  | 2.Deliverables | No more than 7 days late | Between 8 and 28 days late | More than 28 days late
|  | 3.Issues | No more than 7 days late | Between 8 and 28 days late | More than 28 days late
|  | 4.Risks | 5 identified | 4 identified | 0-3 identified
|  | 5.Changes | No more than 7 days late | Between 8 and 28 days late | More than 28 days late
|  | 6.Dependencies | N/A | N/A | N/A
|  | 7.Measures | N/A | N/A | N/A
|  | 8.Communications | At least 1 activity planned AND at least 1 activity this period | No activity planned | No activity this period
|  | 9.Finance | Total PM Estimate = EIF Allocated (H38); AND 20% or less of total EIF spend is allocated to the final quarter | Total PM Estimate = EIF Allocated (H38); AND Between 20 and 30 percent of total EIF spend is allocated to the final quarter | Total PM Estimate does not equal (<>) EIF Allocated (H38); AND/OR more than 30% of total EIF spend is allocated to the final quarter
|  | OVERALL STATUS (Excludes comms and changes) | 0 sections RED AND no more than 1 section AMBER AND Finance AND Deliverables are GREEN | 3 or more sections AMBER; OR Finance or Deliverables are AMBER; OR 1 section RED | 2 or more sections RED

## Data- TO BE HIDDEN (hidden)
Status | Percentage | CommsType | RiskRating | YesNo | EarliestDate | LatestDate | StatusItems | AssetType
open | 0 | e-news | Green | Yes | 2012-01-01 | 2014-12-31 | Pilot | Hardware
closed | 25 | press release | Amber | No |  |  | Production | Software
| 50 | radio item | Red |  |  |  | Out of Service | Document
| 75 | television item | [5 empty] | Other
| 100 | article
event
presentation
social media

## ReportInformation (hidden)
Report No. | Funding? | Report | Start Date | Report Date | Due By | Planned EIF Spend Equipment | Planned EIF Spend Personnel | Planned EIF Spend Other | Planned In-kind Spend Equipment | Planned In-kind Spend Personnel | Planned In-kind Spend Other | Planned Coinvestment Cash Spend Equipment | Planned Coinvestment Cash Spend Personnel | Planned Coinvestment Cash Spend Other | Planned Total EIF | Planned Total Co | Planned cumulative EIF | Planned cumulative co | Planned cumulative total | Actual EIF | Actual Co | Actual Cumulative EIF | Actual Cumulative Coinvestment | Actual Cumulative Total
1 |  |  | 2012-04-12 | 2012-06-01 | 2012-06-15 |  | 52000 |  |  |  | 24000 |  |  |  | 52000 | 24000 | 52000 | 24000 | 76000 | 52000 | 1000 | 52000 | 1000 | 53000
2 |  |  |  | 2012-06-29 | 2012-07-13 |  | 52000 |  |  |  | 49000 |  |  |  | 52000 | 49000 | 104000 | 73000 | 177000 | 52000 | 22679 | 104000 | 23679 | 127679
3 |  |  |  | 2012-07-27 | 2012-08-10 | [9 empty] | 0 | 0 | 104000 | 73000 | 177000 | 0 | 16094 | 104000 | 39773 | 143773
4 |  |  |  | 2012-08-31 | 2012-09-14 |  | 52000 |  |  |  | 14000 |  |  |  | 52000 | 14000 | 156000 | 87000 | 243000 | 20247 | 17116 | 124247 | 56889 | 181136
5 |  |  |  | 2012-11-30 | 2012-12-14 |  | 52000 |  |  |  | 48000 |  |  |  | 52000 | 48000 | 208000 | 135000 | 343000 | 44753 | 57111 | 169000 | 114000 | 283000
6 |  |  |  | 2013-03-01 | 2013-03-15 |  | 52000 | [7 empty] | 52000 | 0 | 260000 | 135000 | 395000 |  |  | 169000 | 114000 | 283000
7 |  |  |  | 2013-05-24 | 2013-06-07 | [9 empty] | 0 | 0 | 260000 | 135000 | 395000 |  |  | 169000 | 114000 | 283000
8 |  |  |  | 2013-08-23 | 2013-09-06 | [9 empty] | 0 | 0 | 260000 | 135000 | 395000 |  |  | 169000 | 114000 | 283000
9 |  |  |  | 2013-11-22 | 2013-12-06 |  | 29000 | [7 empty] | 29000 | 0 | 289000 | 135000 | 424000 |  |  | 169000 | 114000 | 283000
[19 empty] | Total |  |  | 169000 | 114000 | 283000
Values for these fields will now come from Finance 2 cells - ask Judd for advice
Note on U2: The University Of Melbourne: These fields are to come from the database. On creating report 2, report 1 data will be included in the actual EIF and Actual Co row against report 1.

## 10.Assets
1.Header | AMBER
2.Deliverables | RED
3.Issues | GREEN
4.Risks | GREEN
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | AMBER
9.Finance | GREEN
| RT029 | Cloud Based Bioinformatics Tools
| From | 2012-12-01
| To | 2013-03-01
Assets
Complete a row in the table below for any assets delivered
Select a cell for further information.
| Ref | Asset Type | Name | Version Number | Owner/ Custodian | Value | Location | Local Asset Tag | Status
|  | Software | Integrated Billing & Invoicing | 1.1.1 | UWA | 54768 | Atlassian Subversion Repository |  | Production
|  | Software | Questionnaire & LIMS Modules |  | UWA |  | Atlassian Subversion Repository |  | Production
|  | Software | Registry Management Module |  | UWA |  | Atlassian Subversion Repository |  | Production

## Finance 2
| 1.Header | AMBER
| 2.Deliverables | RED
| 3.Issues | GREEN
| 4.Risks | GREEN
| 5.Changes | GREEN
6.Dependencies
7.Measures
| 8.Communications | AMBER
| 9.Finance | GREEN
|  | RT029 | Cloud Based Bioinformatics Tools
|  | From | 2012-12-01
|  | To | 2013-03-01
|  | Finance | [5 empty] | STATUS | GREEN
|  |  |  | Approved Nectar Funds |  |  |  |  | Approved Co-investment
|  | FOR YOUR INFORMATION |  | Total Approved Nectar Funds | Actual Nectar Funds PAID to Project | Actual Project Expenditure Reported | Estimated Cost to complete | Nectar Cash Flow amount to be allocated | Total Approved Co-investment Funds | Actual Co-investment and in-Kind Expenditure Reported | Estimated Co-investment to Complete
|  |  |  | 289000 | 104000 | 152482 | 185000 | 0 | 323892 | 102384 | 221508
[13 empty] | This column holds the values to put in the warning box in row 40 |  |  |  |  | FinanceLight Element | Status
Financial Reporting Period ID | Financial Reporting Period |  | Nectar Funds RECEIVED | Expenditure: Actual Nectar Funds |  |  |  | Project Manager's Nectar Funds FORECAST | Expenditure: Actual Co-investment |  |  | Project Manager's Co-investment FORECAST |  |  | Estimated Project Cash Flow EIF - Shows Actuals where available | Project Manager's Estimated Project Cash Flow Co-investment |  | PM estimate = EIF Allocated | Correct 289000 = 289000 | Total Project Manager's Nectar and Co-investment ACTUAL and FORECASTED Expenditure
| Start Date | End Date |  | Personnel | Equipment | Other | Total |  | Cash Contribution | In-Kind Contribution | Total | [6 empty] | 30% of funds | 86700
1 | 2012-07-01 | 2012-12-31 | 104000 | 122279 | 0 |  | 122279 | 122279 | 2364 | 72474 | 74838 | 74838 |  |  | 122279 | 74838 |  | 30% of funds or more in last quarter | Less than 30% of funds in last quarter: 15552 | 197117
2 | 2013-01-01 | 2013-03-31 |  | 30203 |  |  | 30203 | 30203 |  | 9910 | 9910 | 9910 |  |  | 30203 | 9910 |  | Last Quarter | 15552 | 40113
3 | 2013-04-01 | 2013-06-30 |  |  |  |  | 0 | 60141 | 6000 |  | 6000 | 2825 |  |  | 60141 | 6000 |  | 20% of funds | 57800 | 62966
4 | 2013-07-01 | 2013-09-30 |  |  |  |  | 0 | 60825 | 6000 |  | 6000 | 16637 |  |  | 60825 | 6000 |  | 20% of funds or more in last quarter | Less than 20% of funds in last quarter: 15552 | 77462
5 | 2013-10-01 | 2013-12-31 |  |  |  |  | 0 | 15552 | 5636 |  | 5636 | 4927 |  |  | 15552 | 5636 |  | FINANCE LIGHT | GREEN | 20479
6 | 2014-01-01 | 2014-03-31 |  |  |  |  | 0 | 0 |  |  | 0 | 110637 |  |  | 0 | 110637 |  |  |  | 110637
7 | 2014-04-01 | 2014-06-30 |  |  |  |  | 0 | 0 |  |  | 0 | 110638 |  |  | 0 | 110638 |  |  |  | 110638
8 | 2014-07-01 | 2014-09-30 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
9 | 2014-10-01 | 2014-12-31 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
10 | 2015-01-01 | 2015-03-31 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
11 | 2015-04-01 | 2015-06-30 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
12 | 2015-07-01 | 2015-09-30 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
13 | 2015-10-01 | 2015-12-31 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
|  | TOTAL | 104000 | 152482 | 0 | 0 | 152482 | 289000 | 20000 | 82384 | 102384 | 330412 |  |  | 289000 | 323659
[7 empty] | Nectar Allocated | 289000
Optional Comment
|  |  |  | 2012-12-31 | 2013-03-31 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-03-31 | 2015-06-30 | 2015-09-30 | 2015-12-31 | Total
|  | Nectar Proposal Budget |  | 208000 | 260000 | 260000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000
|  | PM Nectar Forecast |  | 122279 | 30203 | 60141 | 60825 | 15552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289000
|  | PM Nectar Forecast (Accum) |  | 122279 | 152482 | 212623 | 273448 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000
|  | Nectar Actual |  | 122279 | 30203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152482
|  | Nectar Actual (Accum) |  | 122279 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 152482
|  | Nectar Paid (Accum) |  | 104000 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 104000
|  | Co Inv Proposal Budget |  | 66426 | 114892 | 323892 | 323892 | 323892 | 323892 | 323892 | 323892 | 323892 | 323892 | 323892 | 323892 | 323892 | 323892
|  | PM Co inv Forecast |  | 74838 | 9910 | 2825 | 16637 | 4927 | 110637 | 110638 | 0 | 0 | 0 | 0 | 0 | 0 | 330412
|  | PM Co inv Forecast (Accum) |  | 74838 | 84748 | 87573 | 104210 | 109137 | 219774 | 330412 | 330412 | 330412 | 330412 | 330412 | 330412 | 330412 | 102384
|  | Co Inv Actuals |  | 74838 | 9910 | 6000 | 6000 | 5636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102384
|  | Co Inv Actuals (Accum) |  | 74838 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 102384
Note on O19: mecolesm: TO setup the sheet: OPTIONAL A. Modify dates B25-B37 as required. ONLY IF A. CHANGED B. Change named cell "LASTQUARTER" which is currently in H29 if dates are modified above. If the last quarter is modified, then this needs to reflect the new last quarter. (LASTQUARTER is used in the status lights. See columns R and S) ESSENTIAL 1. Add baseline amounts to row 44 and row 50. 2. HIDE rows 43-55 3. HIDE columns M-S 4. Protect Sheet (no password, allow select locked cells; select unlocked cells.) DONE *NOTE the #N/A in rows 48,49,54 are to remove dates not yet passed (based on the end date of the report) from showing in the graphs. They are not errors.