## Sheet1
No. | Funding Milestone | Milestone Title | Deliverables/Completed Activity | Target Milestone Date
1 |  | Sub-contract signed (Linked to Funding Milestone 1) | Sub-contract | When contract signed
2 | Yes | Funding Milestone 1 | Linked to Milestone 1 | When contract signed
3 |  | Established Support Tools & Processes (Linked to Funding Milestone 2) | Support Tools & Processes | 2012-05-15
4 |  | Project Initiation complete (Linked to Funding Milestone 2) | Communications plan prepared and sent to NeCTAR (Signed contract + two months). | 2012-07-01
5 |  | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | Integrate existing application with AAF Authentication Services | 2012-06-14
6 | Yes | Funding Milestone 2 | Linked to Milestone 3, 4 and 5 | 2012-06-14
7 |  | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | Integrated Invoicing & Billing Module | 2012-08-15
8 |  | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | Initial Production Research Cloud Deployment | 2013-03-31
9 | Yes | Funding Milestone 3 | Linked to Milestone 7 and 8 | 2013-03-31
10 |  | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | Data Extraction for Analysis Module | 2013-04-30
11 |  | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | Pedigree Storage & Visualisation Module | 2013-05-10
12 |  | Implemented Registry Management Module (Linked to Funding Milestone 4) | Registry Management Module | 2013-04-30
13 | Yes | Funding Milestone 4 | Linked to Milestone 10, 11 and 12 | 2013-05-10
14 |  | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | Enhanced Data Linkage & Reporting Module | 2013-09-30
15 | Yes | Funding Milestone 5 | Linked to Milestone 13, 14 and 15 Note that all development should be completed by 30 Jan 2012 | 2013-09-30
16 |  | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 6) | Integrate Genotypic Data Management Capability | 2013-11-22
17 | Yes | Funding Milestone 6 | Linked to Milestone 16 Note that all development should be completed by 30 Jan 2012 | 2013-11-22
18 | Yes | Final Admin Closure | Post-implementation Review (PIR) conducted and sent to NeCTAR. | 2013-12-15
|  | (Funding Milestone 7) | Practical Completion Certificate accepted by NeCTAR.
19 |  | Operations to June 2014 | Service Levels met and reported to NeCTAR as defined.