## Sheet1
Updated Schedule as submitted to NeCTAR 13 Feb 2013
No. | Funding Milestone | Milestone Title | Deliverables/Completed Activity | Current Milestone Date | New Milestone Date | Status | Current Module Status
1 |  | Sub-contract signed (Linked to Funding Milestone 1) | Sub-contract | 2012-04-12 | When contract signed | Completed & Signed Off
2 | Yes | Funding Milestone 1 | Linked to Milestone 1 | 2012-04-12 | When contract signed | Completed & Signed Off
3 |  | Established Support Tools & Processes (Linked to Funding Milestone 2) | Support Tools & Processes | 2012-05-15 | 2012-05-15 | Completed & Signed Off
4 |  | Project Initiation complete (Linked to Funding Milestone 2) | Communications plan prepared and sent to NeCTAR (Signed contract + two months). | 2012-07-01 | 2012-07-01 | Completed & Signed Off
5 |  | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | Integrate existing application with AAF Authentication Services | 2012-06-14 | 2012-06-14 | Completed & Signed Off
6 | Yes | Funding Milestone 2 | Linked to Milestone 3, 4 and 5 | 2012-06-29 | 2012-06-14 | Completed & Signed Off
7 |  | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | Integrated Invoicing & Billing Module | 2012-08-15 | 2012-08-15 | Completed & Signed Off
8 |  | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | Initial Production Research Cloud Deployment | 2012-08-15 | 2013-03-31 | Completed & Signed Off
9 | Yes | Funding Milestone 3 | Linked to Milestone 7 and 8 | 2012-08-31 | 2013-03-31 | Completed & Signed Off
10 |  | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | Data Extraction for Analysis Module | 2012-09-30 | 2013-04-30 | Completed & Signed Off
11 |  | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | Pedigree Storage & Visualisation Module | 2012-10-15 | 2013-05-22 | Awaiting completion | Behind Schedule
12 |  | Implemented Registry Management Module (Linked to Funding Milestone 4) | Registry Management Module | 2012-11-30 | 2013-04-30 | Completed & Signed Off
13 | Yes | Funding Milestone 4 | Linked to Milestone 10, 11 and 12 | 2012-12-15 | 2013-05-22 | Completed & Signed Off
14 |  | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | Enhanced Data Linkage & Reporting Module | 2012-12-15 | 2013-09-30 | Completed & Signed Off | Ahead of Schedule
15 | Yes | Funding Milestone 5 | Linked to Milestone 14 | 2013-02-28 | 2013-09-30 | Completed & Ready for Payment | Ahead of Schedule
16 |  | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 6) | Integrate Genotypic Data Management Capability | 2013-03-01 | 2013-11-22
17 | Yes | Funding Milestone 6 | Linked to Milestone 16 | 2013-11-22 | 2013-11-22
18 | Yes | Final Admin Closure | Post-implementation Review (PIR) conducted and sent to NeCTAR. | 2013-11-22 | 2013-12-15
|  | (Funding Milestone 7) | Practical Completion Certificate accepted by NeCTAR. | 2013-11-22
19 |  | Operations to June 2014 | Service Levels met and reported to NeCTAR as defined.