## Sheet1
Milestone | Associated Deliverable Start Date | Milestone Date | EIF Funding | Co-investment Funding |  | Cumulative Expenditure to 1 Dec 12 |  |  | Dec-March |  |  | March-May |  |  | May-August |  |  | Aug-Nov
Sub-contract signed |  | 2012-01-31 |  |  | 2012-12-01 |  |  | 2013-03-31 |  |  | 2013-06-30 |  |  | 2013-09-30 |  |  | 2013-12-31
Funding Milestone 1 |  | 2012-03-31 | 55000
Established Support Tools & Processes | 2012-03-01 | 2012-03-15 | 6944 | 406 | 100% | 6944 | 406 | 100% | 0 | 0 | 100% | 0 | 0 | 100% | 0 | 0 | 100% | 0 | 0
Funding Milestone 2 |  | 2012-03-31 | 55000 | [8 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0
Integrated existing application with AAF Authentication Services | 2012-03-15 | 2012-04-30 | 20833 | 3331 | 100% | 20833 | 3331 | 100% | 0 | 0 | 100% | 0 | 0 | 100% | 0 | 0 | 100% | 0 | 0
Integrated Invoicing & Billing | 2012-03-01 | 2012-06-30 | 14605 | 40163 | 100% | 14605 | 40163 | 100% | 0 | 0 | 100% | 0 | 0 | 100% | 0 | 0 | 100% | 0 | 0
Initial Production Research Cloud Deployed – WARTN – Lisa, Nik | 2012-03-01 | 2012-06-30 | 46911 | 9462 | 75% | 35183.25 | 7096.5 | 100% | 11727.75 | 2365.5 | 100% | 0 | 0 | 100% | 0 | 0 | 100% | 0 | 0
Funding Milestone 3 |  | 2012-06-30 | 55000 | [8 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0
Implemented Data Extraction for Analysis Module | 2012-06-15 | 2012-08-15 | 26680 | 1420 | 50% | 13340 | 710 | 75% | 6670 | 355 | 100% | 6670 | 177.5 | 100% | 0 | 0 | 100% | 0 | 0
Implemented Pedigree Storage & Visualisation Module | 2012-05-01 | 2012-08-30 | 58800 | 11645 | 25% | 14700 | 2911.25 | 25% | 0 | 0 | 100% | 44100 | 2183.4375 | 100% | 0 | 0 | 100% | 0 | 0
Funding Milestone 4 |  | 2012-09-30 | 55000 | [8 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0
Enhanced Data Linkage & Reporting Module – pulling data together? | 2012-09-01 | 2012-11-30 | 37485 | 7424 | 25% | 9371.25 | 1856 | 50% | 9371.25 | 1856 | 75% | 9371.25 | 464 | 100% | 9371.25 | 1856 | 100% | 0 | 0
Implemented Registry Management Module – ie; substudies, etc. | 2012-07-01 | 2012-11-30 | 9736 | 21334 | 75% | 7302 | 16000.5 | 100% | 2434 | 5333.5 | 100% | 0 | 0 | 100% | 0 | 0 | 100% | 0 | 0
Integrated Genotypic Data Management Capability | 2012-08-15 | 2012-12-31 | 68605 | 19708 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 75% | 51453.75 | 14781 | 100% | 17151.25 | 4927
Funding Milestone 5 |  | 2012-12-31 | 55000
Funding Milestone 6 - Final Admin Closure |  | 2013-09-30 | 31000
System Support | 2013-01-01 | 2014-06-30 |  | 189000
Travel Budget (UWA Centre for Genetic Epidemiology and Biostatistics) |  |  |  | 10000
Other Expenses (UWA Research Matching Funds) |  |  |  | 10000
Total EIF Request |  |  | 290598 |  |  | 122278.5 | 72474.25 |  | 30203 | 9910 |  | 60141.25 | 2824.9375 |  | 60825 | 16637 |  | 17151.25 | 4927
[5 empty] | Cumulative |  |  |  | 152481.5 | 82384.25 |  | 212622.75 | 85209.1875 |  | 273447.75 | 101846.1875 |  | 290599 | 106773.1875
[9 empty] | 102617 | 323892 | 221275
110637.5