## D3 INSTRUCTIONS
NeCTAR RFP Stage 2 Part D3 Milestone and Funding Template
INSTRUCTIONS
Step
1 of 8 | Proteomics Virtual Laboratory
2 of 8 | Complete D3.1 Funding Estimate
3 of 8 | Complete D3.2 Milestone Template
4 of 8 | Complete D3.3 Budget Breakdown
5 of 8 | Complete D3.4 Participating Organisations
6 of 8 | Complete D3.5 Fields of Research
7 of 8 | Save the full Excel spreadsheet and send as part of the proposal.
8 of 8 | Also PDF the Excel spreadsheet (ensure D3.1, D3.2, D3.3, D3.4 and D3.5 are each included) and send as part of the proposal. (NOTE: submit 2 docs for D3; Excel and PDF)
Please see example spreadsheet supplied with the pack (Part D3 Milestone and Funding EXAMPLE)
Please add/delete rows as required. Please add comments to each sheet (just type on the sheet outside the table) as required.
Summary of notes for completing each table
D3.1 Funding Estimate
Please add the details of any anticipated participating organisations in the table along with their anticipated Funding Allocation as a percentage of the Proposer’s Total Funding estimate.
D3.2 Milestone Template
Complete the table with proposed milestones and the associated budgets and proposed funding amounts to be drawn down from NeCTAR. The submitted table will be used to prepare the contract Schedules. Deliverables are to be described in as much detail as necessary to show that careful thought has been spent on planning. Funding Milestones should be approximately every six months and linked with deliverables. Milestones should be shown approximately every three months. Please ensure the deliverables match the deliverables listed in Part D2 Response Template B.14 Key Deliverables and Acceptance Criteria. Insert rows as required. You may add comments to the sheet if required.
D3.3 Budget Breakdown
Provide a proposal breakdown of the project budget by the milestones, which are described as an attachment to the Proposal in the format described below. Include proposed staffing levels; where actual individuals have not been allocated to the sub-project, use a role name and Full Time Equivalents (FTE) to show the number and value of budgeted staff that will be working on the sub-project at that milestone. For example; Software Designer by 2 or two Software Designers working full time on the sub-project. Each individual or FTE role is to be included as a separate line item. Break down the budget into EIF (NeCTAR) funding or co-investment funding.
D3.4 Participating Organisations
Please add the details of any anticipated participating organisations. Add extra lines as required. These organisations should match Part D2, Table A.2.2
D3.5 Fields of Research
For RC proposals, this section is optional. VL proposals must complete this section. Select up to five disciplines using either the two of four digit codes, or a mixture of both, and allocate a percentage score or weight against how closely the Proposal is aligned to a particular community discipline or Field of Research. For FOR codes:
http://www.abs.gov.au/AUSSTATS/abs@.nsf/Latestproducts/6BB427AB9696C225CA2574180004463E

## D3.1 Funding Estimate
Proteomics Virtual Laboratory
D3.1 Funding Estimate
Organisation/Group Name | Anticipated distributions of EIF Funds
%
UWA
Total | 0% | review
D3.1 Notes
Please add the details of any anticipated participating organisations in the table along with their anticipated Funding Allocation as a percentage of the Proposer’s Total Funding estimate.
Insert rows as required. You may add comments to the sheet if required.

## D3.2 Milestone Template
Proteomics Virtual Laboratory
D3.2 Milestone Template
No | Funding Milestone Yes/Blank | Milestone Title | Deliverables/Completed Activity | Target Milestone Date | Nectar (EIF) Funds ($) |  |  |  | Co-Investment
[5 empty] | Planned Expenditure Breakdown |  |  | Total Requested ($) | (budgeted contribution value) ('$)
[5 empty] | Labour ($) | Equipment ($) | Other ($)
[5 empty] | (a) | (b) | (c) | (a)+(b)+(c)
1 | Yes | Clinical Proteomics Data Store | The Ark storage mechanism for clinical proteomics data | Q2, 2013 | 51667 |  |  | 51667 | 30925
|  |  | The Ark user interface for proteomics data loading/linking | Q2, 2013 | 25833 |  |  | 25833 | 19925
2 | Yes | Clinical Proteomics Data Extraction & Analysis | The Ark query engine extension for clinical proteomics data | Q4, 2013 | 38750 |  |  | 38750 | 25425
|  |  | The Ark integration with core Proteomics Virtual Laboratory functionality | Q4, 2013 | 38750 |  |  | 38750 | 49775
3 | No | Clinical Proteomics Technical Support | Ongoing The Ark technical support for Proteomics functionality | Q4, 2014 | 0 |  |  | 0 | 39600
0
0
0
0
0
0
0
0
0
0
0
[7 empty] | Sub total | 155000 | 165650
[5 empty] | Total Costs |  |  | 320650
Please ensure that total amounts are consistent with Budget Breakdown (D3.3)
Consistency (D3.2 & D3.3)
[8 empty] | EIF Funds | Co-Invest | Total
D3.2 Notes
Complete the table with proposed milestones and the associated budgets and proposed funding amounts to be drawn down from NeCTAR. The submitted table will be used to prepare the contract Schedules. Deliverables are to be described in as much detail as necessary to show that careful thought has been spent on planning. Funding Milestones should be approximately every six months and linked with deliverables. Milestones should be shown approximately every three months. Please ensure the deliverables match the deliverables listed in Part D2 Response Template B.14 Key Deliverables and Acceptance Criteria. Insert rows as required. You may add comments to the sheet if required.
Please fill in these columns only if it is a funding milestone

## D3.3 Budget Breakdown
Proteomics Virtual Laboratory
D3.3 Budget Breakdown
Milestone No. | Milestone Description | Assigned Resources | Labour |  |  | Equipment ($) | Other ($) | EIF Funding | Co-investment funding
|  |  | FTE | Rate | $ |  |  | ($) | ($) | Contributor
1 | The Ark storage mechanism for clinical proteomics data | Application programmer | 0.33333 | 155000 | 51666.6667 |  |  | 51666.6667 |  |  | review
1 | The Ark storage mechanism for clinical proteomics data | Business Analysts | 0.16667 | 132000 | 22000 |  |  |  | 22000 | UWA | review
1 | The Ark storage mechanism for clinical proteomics data | Subject Matter Expert 1, Subject Matter Expert 2 | 0.05 | 178500 | 8925 |  |  |  | 8925 | Proteomics International, QUD | review
1 | The Ark user interface for proteomics data loading/linking | Application programmer | 0.16667 | 155000 | 25833.3333 |  |  | 25833.3333 |  |  | review |  | 0.8 | 112100
1 | The Ark user interface for proteomics data loading/linking | Business Analysts | 0.083333 | 132000 | 11000 |  |  |  | 11000 | UWA | review |  |  | 49100
1 | The Ark user interface for proteomics data loading/linking | Subject Matter Expert 1, Subject Matter Expert 2 | 0.05 | 178500 | 8925 |  |  |  | 8925 | Proteomics International, QUD | review
2 | The Ark query engine extension for clinical proteomics data | Application programmer | 0.25 | 155000 | 38750 |  |  | 38750 |  |  | review
2 | The Ark query engine extension for clinical proteomics data | Business Analyst | 0.125 | 132000 | 16500 |  |  |  | 16500 | UWA | review
2 | The Ark query engine extension for clinical proteomics data | Subject Matter Expert 1, Subject Matter Expert 2 | 0.05 | 178500 | 8925 |  |  |  | 8925 | Proteomics International, QUD | review
2 | The Ark integration with core Proteomics Virtual Laboratory functionality | Application programmer | 0.25 | 155000 | 38750 |  |  | 38750 |  |  | review
2 | The Ark integration with core Proteomics Virtual Laboratory functionality | Business Analyst | 0.125 | 132000 | 16500 |  |  |  | 23000 | UWA | review
2 | The Ark integration with core Proteomics Virtual Laboratory functionality | Subject Matter Expert 1, Subject Matter Expert 2, Subject Matter Expert 3 | 0.15 | 178500 | 26775 |  |  |  | 26775 | Proteomics International, QUD | review
3 | Ongoing The Ark technical support for Proteomics functionality | Technical Support Officer | 0.3 | 132000 | 39600 |  |  |  | 39600 | UWA | review
review
|  |  | Subtotal |  | 314150 | 0 | 0 | 155000 | 165650 | review
[8 empty] | 320650 |  | TOTAL
Please ensure subtotals and total are consistent with Milestone Template (D3.2)
D3.3 Notes
Provide a proposal breakdown of the project budget by the milestones in the format above. Include proposed staffing levels; where actual individuals have not been allocated to the sub-project, use a role name and Full Time Equivalents (FTE) to show the number and value of budgeted staff that will be working on the sub-project at that milestone. For example; Software Designer by 2 or two Software Designers working full time on the sub-project. Each individual or FTE role is to be included as a separate line item. Break down the budget into EIF (NeCTAR) funding or co-investment funding. Insert rows as required. You may add comments to the sheet if required. | [11 empty] | 53150

## D3.4 Participating Organisation
Proteomics Virtual Laboratory
D3.4 Participating Organisations
Organisation/Group Name | State | Role
Macquarie University | NSW | Applicant, Contributor, Supporter, Beneficiary
Adelaide Proteomics Centre* | South Australia | Supporter, Beneficiary
Australasian Proteomics Society | All Australia | Supporter, Beneficiary
Australian Proteome Analysis Facility* | NSW | Contributor, Supporter, Beneficiary
Bioplatforms Australia | All Australia | Supporter, Beneficiary
CSIRO | All Australia | Contributor, Supporter, Beneficiary
EMBL Australia | Victoria & Queensland | Supporter, Beneficiary
Garvan Institute for Medical Research | NSW | Contributor, Supporter, Beneficiary
Genomics Virtual Lab, University of Queensland | Queensland | Contributor, Supporter, Beneficiary
Hunter Medical Research Institute | NSW | Supporter, Beneficiary
Intersect | NSW | Contributor, Supporter, Beneficiary
Monash Antibody Technologies Facility* | Victoria | Supporter, Beneficiary
Monash Biomedical Proteomics Facility* | Victoria | Supporter, Beneficiary
Monash University | Victoria | Contributor, Supporter, Beneficiary
Proetomics Australia | All Australia | Supporter, Beneficiary
Queensland Institute of Medical Research* | Queensland | Supporter, Beneficiary
Queensland University of Technology | Queensland | Contributor, Supporter, Beneficiary
TGR BioSciences* | South Australia | Supporter, Beneficiary
University of Western Australia | Western Australia | Contributor, Supporter, Beneficiary
NSW Systems Biology Initiative (UNSW) | NSW | Supporter, Beneficiary
Victorian Life Science Computational Initiative | Victoria | Supporter, Beneficiary
WAIMR, Proteomics International* | Supporter, Beneficiary | Supporter, Beneficiary
Wound Management Innovation CRC | All Australia | Supporter, Beneficiary

## D3.5 Fields of Research
Virtual Proteomics Laboratory
D3.5 Fields of Research
DISCIPLINE/FOR Code | Weight (percent)
060109 Proteomics and Intermolecular Interactions (excl. Medical Proteomics) | 30%
110106 Medical Biochemistry: Proteins and Peptides (incl. Medical Proteomics) | 30%
111202 Cancer Diagnosis | 15%
110309 Infectious Diseases | 15%
110702 Applied Immunology (incl. Antibody Engineering, Xenotransplantation and T-cell Therapies) | 10%
100%
For RC proposals, this section is optional. VL proposals must complete this section. Select up to five disciplines using either the two or four digit codes, or a mixture of both, and allocate a percentage score or weight against how closely the Proposal is aligned to a particular community discipline or Field Of Research. The FOR codes are available at:
http://www.abs.gov.au/AUSSTATS/abs@.nsf/Latestproducts/6BB427AB9696C225CA2574180004463E