## Sheet1
| Start Date | Completed | Remaining
Familiarization with the project | 2013-03-20 | 60 | 0
Ark-pedigree module design and development | 2013-04-01 | 160 | 0
Ark-pedigree module testing and enhancements | 2013-10-15 | 25 | 0
Create literature review topics | 2013-05-01 | 30 | 0
Literature review | 2013-06-01 | 240 | 100
Form research questions | 2013-09-01 | 30 | 0
GWAS data experiment part I | 2013-10-15 | 20 | 0
GWAS data experiment part II | 2014-03-20 | 0 | 30
Prepare SPARK abstract for ICG-8 conference | 2013-09-15 | 15 | 0
SPARK overview - 1 page paper | 2013-11-01 | 60 | 0
Pedigree - 4-page paper | 2014-04-01 | 0 | 60
Prepare confirmation report and presentation | 2013-12-15 | 97 | 0
Data management - full paper | 2014-05-01 | 0 | 60
Design and implement SPARK GWAS data management | 2014-06-01 | 0 | 120
Design and implement parallel versions of existing GWAS analyses | 2014-08-01 | 0 | 120
Parallel versions of GWAS analyses - full paper | 2014-10-01 | 0 | 75
Design and implement the SPARK supercomputer web interface | 2014-10-01 | 0 | 150
Migrate the Twins & Sisters study data | 2015-03-01 | 0 | 30
The fit of Twins & Sisters to SPARK - 4-page paper | 2015-04-01 | 0 | 60
Test and evaluvate system performance | 2015-04-01 | 0 | 120
GWAS systems - literature review paper | 2015-06-01 | 0 | 60
SPARK - full journal paper | 2015-08-01 | 0 | 60
SPARK WIP | 2016-01-01 | 0 | 45
Thesis write up | 2015-09-01 | 0 | 203