## AugustGuess
version	features/aims	Atlassian Estimates based Guess in dev days	notes	DEV day total	human date guess

“1.1.1”	Core functionality	0
“1.1.2”	Registry/Billing	0	should be zero (all closed in atlassian)...needs updating
1.1.1a	Core functionality	6	all testing time only. Maybe 60% of this testing could be done by non-dev team. Can also be done in parallel	6	parallel work can happen while we do other tasks?
1.1.1b	Stability and core features	11.2		17.2	09/09/12
1.1.1c	Stability and core features	16.675		33.875	20/09/12
1.1.1d	Data extraction module/functionality	40		73.875	20/10/12
1.1.1e	Getting prod env ready and transfering WAGER data/setting/ldap to prod	44	the more hands on deck testing: the less dev time for this.	117.875	20/11/12	this magical number allows for very little testing really...or for the inevitable bugs picked up in testing. The more help we get from now until the release day, the better to make sure peoples data is going to be as expected

“1.1.3”	Geneological Family etc, base strutcture, data transfer and visualisation	60	40 days is our guess for base structure and importing data. Crazy loose guess at 20 days for some kind of linking to a visualisation solution	177.875	07/01/13	Trav will be away about 4 weeks, but could do some work remotely. Plus whatever holidays everyone else takes

“1.1.5”	Genotypic basic linking, storage and/or execution	50	mad guess...depends what is required	227.875	12/02/13	depends on trav & thilinas hours per week...the estimate its so crass given what is required is very undefined right now
“1.1.6”	Enhanced data linkage and reporting	40	I wont even claim to have a decent guess at this...jsut throwing a number out there... what is this?	267.875	10/03/13	guesses are starting to get meaningless
“2.0.0”	feature requests and things like test scripts	56	this stuff may sneak up???	323.875	20/04/13
“3.0.0”	optomistic feature requests	16	this stuff may sneak up???	339.875	01/05/13
1.1.1b-admin	admin tasks not for developers	n\a	hopefully this is parallel to development	339.875	n/a
“1.1.4”	OLD Data extraction module/functionality project	ZERO...moved up above to make logical order		n/a

## PedB4Prd
THIS VERSION IS PUTTING PEDIGREE BEFORE PROD RELEASE TO MEET FUNDING DEADLINES
version	features/aims	Atlassian Estimates based Guess in dev days	notes	DEV day total	human date guess

“1.1.1”	Core functionality	0
“1.1.2”	Registry/Billing	0	should be zero (all closed in atlassian)...needs updating
1.1.1a	Core functionality	6	all testing time only. Maybe 60% of this testing could be done by non-dev team. Can also be done in parallel	6	parallel work can happen while we do other tasks?
1.1.1b	Stability and core features	9.75		15.75	11/09/12
1.1.1c	Stability and core features	16.675		32.425	20/09/12
1.1.1d	Data extraction module/functionality	40		72.425	20/10/12
“1.1.5”	Genotypic basic linking, storage and/or execution	50	mad guess...depends what is required	122.425	23/11/12	depends on trav & thilinas hours per week...the estimate its so crass given what is required is very undefined right now
1.1.1e	Getting prod env ready and transfering WAGER data/setting/ldap to prod	44	the more hands on deck testing: the less dev time for this.	166.425	06/01/13	this magical number allows for very little testing really...or for the inevitable bugs picked up in testing. The more help we get from now until the release day, the better to make sure peoples data is going to be as expected	Could sneak in before Xmas break, might sneak in after???

“1.1.5”	Genotypic basic linking, storage and/or execution	50	mad guess...depends what is required	216.425	12/02/13	depends on trav & thilinas hours per week...the estimate its so crass given what is required is very undefined right now
“1.1.6”	Enhanced data linkage and reporting	40	I wont even claim to have a decent guess at this...jsut throwing a number out there... what is this?	256.425	10/03/13	guesses are starting to get meaningless
“2.0.0”	feature requests and things like test scripts	56	this stuff may sneak up???	312.425	20/04/13
“3.0.0”	optomistic feature requests	16	this stuff may sneak up???	328.425	01/05/13
1.1.1b-admin	admin tasks not for developers	n\a	hopefully this is parallel to development	328.425	n/a
“1.1.4”	OLD Data extraction module/functionality project	ZERO...moved up above to make logical order		n/a

## quicklyAccross
THIS VERSION IS DISCUSSED WITH PAUL MON 3rd Sept. Aim is to get data across ASAP, and offer support with reports, etc, and in doing so we then figure out extract requirements etc.
version	features/aims	Atlassian Estimates based Guess in dev days	notes	DEV day total	human date guess

“1.1.1”	Core functionality	0
“1.1.2”	Registry/Billing	0	should be zero (all closed in atlassian)...needs updating
1.1.1a	Core functionality	6	all testing time only. Maybe 60% of this testing could be done by non-dev team. Can also be done in parallel	6	parallel work can happen while we do other tasks?
1.1.1b	Stability and core features	6		12	11/09/12
1.1.1c	Stability and core features	17.75		29.75	22/09/12
1.1.1e	Getting prod env ready and transfering WAGER data/setting/ldap to prod	44	the more hands on deck testing: the less dev time for this. Paul recommends Chris to approach most of this on his own while I continue on coding	163.75	17/11/12	this magical number allows for very little testing really...or for the inevitable bugs picked up in testing. The more help we get from now until the release day, the better to make sure peoples data is going to be as expected	Could sneak in before Xmas break, might sneak in after???

1.1.1d	Data extraction module/functionality	40	Travis doing this in parallel with Chris doing the data move	73.75	20/11/12
“1.1.5”	Genotypic basic linking, storage and/or execution	50	mad guess...depends what is required	113.75	23/11/12	depends on trav & thilinas hours per week...the estimate its so crass given what is required is very undefined right now

“1.1.5”	Genotypic basic linking, storage and/or execution	50	mad guess...depends what is required	213.75	12/02/13	depends on trav & thilinas hours per week...the estimate its so crass given what is required is very undefined right now
“1.1.6”	Enhanced data linkage and reporting	40	I wont even claim to have a decent guess at this...jsut throwing a number out there... what is this?	253.75	10/03/13	guesses are starting to get meaningless
“2.0.0”	feature requests and things like test scripts	56	this stuff may sneak up???	309.75	20/04/13
“3.0.0”	optomistic feature requests	16	this stuff may sneak up???	325.75	01/05/13
Unscheduled	Scary bunch of tasks we are not sure about yet	21.5		347.25	?????
1.1.1b-admin	admin tasks not for developers	n\a	hopefully this is parallel to development	347.25	n/a
“1.1.4”	OLD Data extraction module/functionality project	ZERO...moved up above to make logical order		n/a